## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Preparation and submission of Detailed Project Report of DADPUR DIGHIRPAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000161/2021-2022 | 1915/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.62 | 2.61 | 99.57 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for DADPUR DIGHIRPAR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000095/2022-2023 | 1207/SWD-I | 02/09/2022 | 02/10/2022 | MAMON ENTERPRISE AND CONSTRUCTION | 20.06 | 19.32 | 96.29 | 100
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Construction of chlorination room at DADPUR DIGHIRPAR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012523] | AE BSD |  | ORD/000123/2022-2023 | 1291/SWD-I | 14/09/2022 | 13/11/2022 | SANJAY ENTERPRISE | 5.47 | 4.64 | 84.83 | 100
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Payment of electric bill of security deposit for New service connection under SMD, PHE Dte. |  |  | BILL/01482/2022-2023 | BP-2022-23-448 | 17/03/2023 |  | WBSEDCL | 4.06 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 294/SWD-I | 25/04/2023 |  | Resource Division | 6.7 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at DADPUR DIGHIRPAR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 911) | AE BSD |  | ORD/000203/2022-2023 | 1559/SWD-I | 13/10/2022 | 11/01/2023 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 178.64 | 107.2 | 60.01 | 60
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Dadpur Dighirpar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000275/2022-2023 | 3919/SMD | 30/12/2022 | 30/03/2023 | BISALAXMI ENTERPRISE | 13.04 | 12.4 | 95.09 | 100
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/12053 | Augmentation | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/12053) |  |  | ORD/000337/2024-2025 | 3311/SWD-I | 23/07/2024 | 06/09/2024 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 62.15 | 0 | 0 | 0
Total | [13 empty] | 292.75 | 146.16 | 49.93