## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for RAMGOPALPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000092/2022-2023 | 1204/SWD-I | 02/09/2022 | 02/10/2022 | PAPPU ENTERPRISE | 20.06 | 16.83 | 83.9 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Preparation and submission of Detailed Project Report of RAMGOPALPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000205/2021-2022 | 1918/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.62 | 2.46 | 94.09 | 100
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Construction of chlorination room at RAMGOPALPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012521] | AE BSD |  | ORD/000120/2022-2023 | 1288/SWD-I | 14/09/2022 | 13/11/2022 | LAKSHMI IRON | 5.44 | 4.4 | 80.93 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000273/2023-2024 | 2418/SWD-I | 30/09/2023 |  | Resource Division | 4.19 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000337/2023-2024 | 270/SWD-I | 10/01/2024 |  | Resource Division | 3.04 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Balance miscellaneous work for Ground water based RAMGOPALPUR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12058) |  |  | ORD/000907/2023-2024 | 1206/SWD-I | 11/03/2024 | 25/04/2024 | S.S. CONSULTANCY & CONSTRUCTION | 21.03 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Additional work for Sinking of 01 (One) no. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for RAMGOPALPUR PWSS of BARUIPUR Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/012521] | AE BSD | JE-2 | ORD/000454/2023-2024 | 2109/SWD-I | 30/08/2023 | 14/09/2023 | PAPPU ENTERPRISE | 2.2 | 0 | 0 | 100
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Construction of Platform for providing FHTC for Ground Water Based RAMGOPALPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12058) |  |  | ORD/000308/2024-2025 | 3221/SWD-I | 18/07/2024 | 16/09/2024 | MONDAL CONSTRUCTION (BARUIPUR) | 10.46 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at RAMGOPALPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [Nos of FHTC- 566] | AE BSD | JE-1 | ORD/000098/2022-2023 | 1209/SWD-I | 02/09/2022 | 01/12/2022 | MONDAL CONSTRUCTION | 91.26 | 80.44 | 88.14 | 98
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Tripura Nagar (Ramgopalpur) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002204/2023-2024 | 1422/SMSD | 21/11/2023 | 06/12/2023 | COOLING CARE CENTER | 0.9 | 0.67 | 74.91 | 100
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of of Tripuranagar (Ramgopalpur) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12058) | Assistant Engineer | Junior Engineer | ORD/002793/2023-2024 | 1628/SMSD | 29/12/2023 | 13/01/2024 | COOLING CARE CENTER | 0.29 | 0 | 0 | 100
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based Tripura Nagar (RAMGOPALPUR) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Par | SM/12058 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Tripura Nagar (Ramgopalpur) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000470/2022-2023 | 3941/SMD | 30/12/2022 | 30/03/2023 | COOLING CARE CENTER | 11.19 | 5.33 | 47.68 | 100
Total | [13 empty] | 172.68 | 110.14 | 63.78