## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Preparation and submission of Detailed Project Report of GANESHPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000160/2021-2022 | 1921/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 3.03 | 2.66 | 87.61 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Construction of 03 (Three) nos. chlorination room at GANESHPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012659] | AE BSD |  | ORD/000118/2022-2023 | 1286/SWD-I | 14/09/2022 | 13/11/2022 | M/S. SREEJIT ENTERPRISE | 16.38 | 4.41 | 26.94 | 33
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Ganeshpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000459/2022-2023 | 3936/SMD | 30/12/2022 | 30/03/2023 | S.G.ENTERPRISE | 29.99 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000266/2023-2024 | 2421/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 44.65 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/00004/2023-2024 | BP-2023-24-38 | 18/05/2023 | 18/05/2023 | WBSEDCL | 2.01 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/00376/2023-2024 | BP-2023-24-38 | 18/05/2023 | 18/05/2023 | WBSEDCL | 0.73 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Payment of Electric Bill for new service connection under SMD PHE Dte. |  |  | BILL/00281/2023-2024 |  | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.73 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Sinking of 03 (three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GANESHPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD | JE-2 | ORD/000094/2022-2023 | 1206/SWD-I | 02/09/2022 | 02/10/2022 | JEWS CONSTRUCTION AND CO | 60.07 | 39.69 | 66.08 | 67
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000335/2023-2024 | 265/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 13.76 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, 2 and 3 of Ganeshpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000411/2023-2024 | 2505/SMD | 17/07/2023 | 01/08/2025 | S.G.ENTERPRISE | 37.83 | 11.74 | 31.02 | 40
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at GANESHPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 2233) | AE BSD | JE-2 | ORD/000223/2022-2023 | 1657/SWD-I | 21/10/2022 | 07/06/2025 | PATHIK PABAN NANDI | 262.37 | 190.5 | 72.61 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for Proposed Ground Water based GANESHPUR piped water supply schee to accoodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12061) (2nd call) | AE BSD |  | ORD/000731/2024-2025 | 4618/SWD-I | 13/11/2024 | 14/01/2026 | PINKI CONSTRUCTION | 91.61 | 0 | 0 | 30
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-2 & 3 of Ganeshpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12061) | Assistant Engineer | Junior Engineer | ORD/000361/2025-2026 | 709/SMSD | 15/05/2025 | 30/05/2025 | S.G.ENTERPRISE | 0.58 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ganeshpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12061) | Assistant Engineer | Junior Engineer | ORD/000362/2025-2026 | 693/SMSD | 15/05/2025 | 30/05/2025 | S.G.ENTERPRISE | 0.88 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GANESHPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12061 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Ganeshpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12061) | Assistant Engineer | Junior Engineer | ORD/000363/2025-2026 | 694/SMSD | 15/05/2025 | 30/05/2025 | S.G.ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 565.5 | 249.01 | 44.03