## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12204 | Augmentation | Construction of Boundary wall for proposed OHR Site of Zone-IV within Mandirbazar block, Mouza-Dhopahat (JL No-119), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas under South 24-Pgns. W/S Division-I, PHE Dte. (Length- 160 mtr.) | AE HQ-I | JE-3 | ORD/000727/2022-2023 | 190/SWD-I | 26/04/2022 | 25/06/2022 | M/S. KALPANA CONSTRUCTION | 21.75 | 21.69 | 99.73 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12204 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of DHOPA HAT MOUZA in MANDIRBAZAR (ZONE-IV) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000390/2021-2022 | 1986/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 4 | 2.91 | 72.85 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12204 | Augmentation | Construction of 300 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-IV at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2270) | AE HQ-I | JE-3 | ORD/000712/2022-2023 | 3528/SWD-I | 17/03/2023 | 11/01/2024 | SUPER SKILL | 458.61 | 144.44 | 31.5 | 25
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12204 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 3016/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 2.74 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12204 | Augmentation | Construction of Approach Road for Head Work Site (Dhoparhat) at Zone-IV for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-IV at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District-South 24-Pgns. underSouth 24-Pgns. W/S Division-I, PHE Dte. (SM/12204) | AE HQ-I | JE-3 | ORD/000757/2023-2024 | 658/SWD-I | 06/02/2024 | 22/02/2025 | M/S SUBHODEEP ENTERPRISE | 19.75 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12204 | Augmentation | Protection of pipe line and other allied work for laying of distribution pipes in between Zone X and Zone IV under Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone IV at Mandirbazar block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/12204) |  |  | ORD/001131/2024-2025 | 194/SWD-I | 17/01/2025 | 03/03/2025 | BISWAS CONSTRUCTION | 26.73 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-IV AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12204 | Augmentation | WATER MAIN PIPE LINE UNDER RAILWAY TRACK INBETWEEN MADHABPUR STATION AND LAKSHMIKANTAPUR STATION (name of work) at Km MAST NO:- 59/29, 59/31 AND MAST NO:- 59/30,59/32 Section across/through Railway land for a length of meters 57.02 sq m vide Railway Plan No. 42/L/ 2024 |  |  | BILL/00045/2025-2026 |  | 09/04/2025 | 09/04/2025 | EASTERN RAILWAY SEALDAH DIVISION | 5.42 | 0 | 0 | 0
Total | [13 empty] | 538.99 | 169.04 | 31.36