## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Construction of Boundary wall for proposed OHR Site of Zone-VI within Mandirbazar block, Mouza-Shibpur (JL No-59), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas under South 24 Pgns. Water Supply Division-I, PHE Dte. (Length- 110 mtr.) | AE HQ-I | JE-3 | ORD/000072/2022-2023 | 1153/SWD-I | 26/08/2022 | 25/10/2022 | ARYA ENGINEERS | 15.32 | 13.04 | 85.11 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of SHIBPUR MOUZA in MANDIRBAZAR (ZONE-VI) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000392/2021-2022 | 2603/SWD-I | 15/03/2022 | 14/04/2022 | MS R. DUTTA AND CO | 4.62 | 3.13 | 67.79 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 3016/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 2.74 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Construction of Approach Road with Land Development and construction of Boundary Wall gate to facilitate the works within Head Work Site under the Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-VI at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme Water Based Water Supply Scheme for Falta-Mathurapur, Dist- South 24-Pgns." under South 24-Pgns. W/S Divn.-I, PHE Dte. (TSM/014544) | AE HQ-I | JE-3 | ORD/000619/2023-2024 | 2803/SWD-I | 09/11/2023 | 24/12/2023 | M/S SUBHODEEP ENTERPRISE | 5.82 | 5.44 | 93.37 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Wayleave Facility Charge (Station From-To Lakshmikantapur (LKPR) - Udairampur Halt (URP)) (Revenue Village Lakshmikantapur) |  |  | BILL/00102/2024-2025 | BP-2024-25-85 | 22/05/2024 | 22/05/2024 | EASTERN RAILWAY SEALDAH DIVISION | 5.38 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Permanent Restoration work of probable Black top damage which would caused due to laying of PHED pipe (Falta-Mathurapur Mega surface water supply scheme of PHED) on Purbabishnupur-Lakshmikantapur-Kulpi Road at Dayarampur (Ch. 10.33 kmp.), Raghunathpur (Ch. 11.55 kmp.) Madhusudanpur (Ch. 12.65 kmp.), Tantirhat (Ch.13.15 kmp.) and Mollarchak (Ch. 13.80 kmp.), under Diamond Harbour Division,P.W.Dte. in the district of South 24 Pgs. (SM/12205) |  |  | BILL/00683/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 7.66 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-VI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (TSM/014544) [5th SLSSC (2022-23)] | AE HQ-I | JE-3 | ORD/000771/2022-2023 | 3645/SWD-I | 28/03/2023 | 27/04/2025 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 328.19 | 207.31 | 63.17 | 60
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-VI AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN | SM/12205 | Augmentation | Construction of 400 cum capacity Over Head Reservoir as per Departmental Drawing and specifications including RCC bored pile and pile cap within Zone-VI at Shibpur Mouza of Mandirbazar Block, for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24 Pgs District, under South 24 Pgns Water Supply Divn.-I, PHE Dte. (TSM/014544) | AE HQ-I | JE-3 | ORD/000308/2023-2024 | 1697/SWD-I | 07/08/2023 | 01/05/2025 | M/S SUBHODEEP ENTERPRISE | 133.72 | 110.29 | 82.48 | 20
Total | [13 empty] | 503.46 | 339.21 | 67.38