## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Preparation and submission of Detailed Project Report of ARUNNAGAR DAKSHIN Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000207/2021-2022 | 1933/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 3.03 | 2.65 | 87.45 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 3424/SWD-I | 13/03/2023 |  | Resource Division | 7.77 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 338/SWD-I | 26/04/2023 |  | Resource Division | 22.3 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Arun Nagr Dakshin water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000574/2022-2023 | 599/SMD | 27/02/2023 | 28/05/2023 | AHALYA ENGINEERING WORKS | 23.98 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for ARUNNAGAR DAKSHIN PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the arsenic Affected Areas of South 24 Pgs district. [TSM/014830] [2nd Call] | AE BSD | JE-2 | ORD/000681/2022-2023 | 3481/SWD-I | 15/03/2023 | 14/04/2023 | KHANDAKAR CONSTRUCTION | 31.75 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Laying distribution system, Rising Main, Functional House Hold Tap Connection (FHTC) alongwith construction of Chlorine Room (two nos.) for augmentation of ARUN NAGAR DAKSHIN Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [No. of FHTC = 1261] [TSM/014830] | AE BSD | JE-2 | ORD/000814/2022-2023 | 3722/SWD-I | 31/03/2023 | 29/06/2023 | BARI ENTERPRISE | 275.49 | 67.88 | 24.64 | 55
Total | [13 empty] | 364.33 | 70.53 | 19.36