## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Preparation and submission of Detailed Project Report of ARUNNAGAR DAKSHIN Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000207/2021-2022 | 1933/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 3.03 | 2.65 | 87.45 | 100
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Arun Nagr Dakshin water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000574/2022-2023 | 599/SMD | 27/02/2023 | 28/05/2023 | AHALYA ENGINEERING WORKS | 23.98 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 338/SWD-I | 26/04/2023 | 26/04/2023 | Resource Division | 22.3 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 3424/SWD-I | 13/03/2023 | 13/03/2023 | Resource Division | 7.77 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for ARUNNAGAR DAKSHIN PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the arsenic Affected Areas of South 24 Pgs district. [TSM/014830] [2nd Call] | AE BSD | JE-2 | ORD/000681/2022-2023 | 3481/SWD-I | 15/03/2023 | 14/04/2023 | KHANDAKAR CONSTRUCTION | 31.75 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Construction of Boundary wall, Platform for providing FHTC, protection wall for laying pipeline and other allied works for Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12208) | AE BSD | JE-2 | ORD/000770/2024-2025 | 4746/SWD-I | 20/11/2024 | 19/05/2025 | S P ENTERPRISE (MURSHIDABAD) | 80.92 | 0 | 0 | 40
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12208 | Augmentation | Additional work for Sinking of 02 (Two) nos. Rig ground bored 250mm X 150mm dia Tubewell having 66 mtr. housing to achieve 360 mtr. deep Tubewell by Rotary method for ARUN NAGAR DAKSHIN PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/12208] | AE BSD | JE-2 | ORD/000710/2024-2025 | 4540/SWD-I | 06/11/2024 | 21/11/2024 | KHANDAKAR CONSTRUCTION | 4.73 | 0 | 0 | 100
Total | [13 empty] | 174.49 | 2.65 | 1.52