## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BADEHUGLI Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I |  | ORD/000265/2022-2023 | 1776/SWD-I | 07/11/2022 | 07/12/2022 | TAPAS KUMAR GIRI | 30.07 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube-well to achieve 66 mtr. housing pipe by Rotary Method for BADEHUGLI PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12209] | AE HQ-I |  | ORD/000736/2022-2023 | 3574/SWD-I | 22/03/2023 | 06/04/2023 | TAPAS KUMAR GIRI | 3.14 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 13.62 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000227/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 6.13 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at head work site for BADEHUGLI PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12209] | AE HQ-II | JE-3 | ORD/000768/2023-2024 | 777/SWD-I | 13/02/2024 | 28/02/2024 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Charges for New service connection at Badehoogly Pump house-1 |  |  | BILL/00214/2024-2025 | BP-2024-25-71 | 16/05/2024 | 16/05/2024 | WBSEDCL | 4.42 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 995] | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000514/2022-2023 | 2944/SWD-I | 16/02/2023 | 02/11/2025 | MAJUMDER ENTERPRISE | 299.69 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Badehugli water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000870/2022-2023 | 363/SMD | 10/02/2023 | 01/04/2025 | SANKAR PRASAD DUTTA & CO. | 26.54 | 0 | 0 | 40
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Construction of Boundary Wall , Pathway, Drain & others allied works at HW Site of " BADEHUGLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/12209) [2nd call] | AE HQ-I,AE HQ-II,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000405/2024-2025 | 3683/SWD-I | 22/08/2024 | 01/05/2025 | MAJUMDER ENTERPRISE | 40.94 | 0 | 0 | 20
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Badehugli W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/12209) | Assistant Engineer | Junior Engineer | ORD/001173/2024-2025 | 1661/SMSD | 13/12/2024 | 28/12/2024 | SANKAR PRASAD DUTTA & CO. | 0.91 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Badehugli W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/12209) | Assistant Engineer | Junior Engineer | ORD/001174/2024-2025 | 1660/SMSD | 13/12/2024 | 28/12/2024 | SANKAR PRASAD DUTTA & CO. | 0.58 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12209) |  |  | ORD/000141/2025-2026 | 2247/SWD-I | 02/09/2025 | 17/10/2025 | RIMON ENTERPRISE | 10.04 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BADEHUGLI piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12209 | Augmentation | Land development at Badehugli Head Work Site within Poleghat Gram Panchayet under Sonarpur Block for "Ground Water Based BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12209) [2nd call] | AE HQ-II,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000797/2023-2024 | 1145/SWD-I | 07/03/2024 | 01/05/2025 | MAJUMDER ENTERPRISE | 11.01 | 0 | 0 | 100
Total | [13 empty] | 462.97 | 0 | 0