## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BARAGACHHIA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I |  | ORD/000264/2022-2023 | 1772/SWD-I | 07/11/2022 | 07/12/2022 | TAPAS KUMAR GIRI | 30.07 | 13.59 | 45.2 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Bara Gachhia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000293/2022-2023 | 452/SMD | 17/02/2023 | 01/07/2026 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 23.38 | 10.66 | 45.58 | 60
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BARAGACHHIA PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12211] | AE HQ-I |  | ORD/000764/2022-2023 | 3603/SWD-I | 24/03/2023 | 08/04/2023 | TAPAS KUMAR GIRI | 3.14 | 1.57 | 50 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023) | AE HQ-II |  | ORD/000182/2023-2024 | 774/SWD-I | 31/05/2023 | 30/11/2023 | INDRADEV JHA | 0.87 | 2.27 | 261.44 | 30
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BARAGACHHIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1892] | AE HQ-I,Assistant engineer (contractual) | JE RWS, Sonarpur Block | ORD/000112/2023-2024 | 524/SWD-I | 11/05/2023 | 02/01/2026 | M/S R.K. ENTERPRISE | 500.51 | 97.81 | 19.54 | 50
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte."(w.e.f. 01/12/2023 to 31/05/2024) | AE HQ-II | JE-3 | ORD/000705/2023-2024 | 3001/SWD-I | 29/11/2023 | 30/05/2024 | INDRADEV JHA | 0.87 | 2.39 | 274.6 | 10
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 19.21 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000250/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 11.65 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01108/2023-2024 | BP-2023-24-153 | 24/07/2023 | 24/07/2023 | WBSEDCL | 4.52 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte."(w.e.f. 01/06/2024 to 30/11/2024) [Vehicle No- WB-04F-8738] | AE HQ-II | JE-2,JE-3 | ORD/000217/2024-2025 | 2451/SWD-I | 24/05/2024 | 23/11/2024 | INDRADEV JHA | 0.87 | 2.19 | 251.7 | 50
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Renovation of Pump house, Chlorine room, Office room, Construction of Pathway at existing OHR site of Baragachhia Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pargnas District under Jal Jeevan Mission. (SM/12211) |  |  | ORD/000701/2024-2025 | 4503/SWD-I | 30/10/2024 | 14/12/2024 | ISHIYA ENTERPRISE | 20.73 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Construction of Boundary Wall, Pathway,Drain, Development of Land & others allied works at HW Site of "BARAGACHHIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12211) [2nd call] |  |  | ORD/000408/2024-2025 | 3705/SWD-I | 23/08/2024 | 07/10/2024 | M/S R.K. ENTERPRISE (BARASAT) | 48.08 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bara Gachhia W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002342/2023-2024 | 263/SMSD | 23/02/2024 | 09/03/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of BARAGACHHIA Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/12211] | Assistant engineer (contractual) | JE-3 | ORD/001099/2024-2025 | 75/SWD-I | 07/01/2025 | 09/03/2025 | AQUATECH ENGINEERS | 15.5 | 7.91 | 51.05 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BARA GACHHIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12211 | Augmentation | Charges for Load Enhancement at pump house no- II of Bargachia water supply scheme.(Sonarpur Block) |  |  | BILL/00494/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
Total | [13 empty] | 680.54 | 138.38 | 20.33