## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Construction of 02 (Two) nos. chlorination room at BIRALDHAM NAGAR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014396] | AE BSD |  | ORD/000127/2022-2023 | 1299/SWD-I | 14/09/2022 | 13/11/2022 | M/S. ARPAN ENTERPRISE. | 10.91 | 0 | 0 | 50
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Biraldham Nagar PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014396] | AE BSD |  | ORD/000790/2022-2023 | 3669/SWD-I | 29/03/2023 | 13/04/2023 | CAPITAL CONSTRUCTION | 4.4 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Preparation and submission of Detailed Project Report of BIRALDHAM NAGAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000357/2021-2022 | 1959/SWD-I | 27/01/2022 | 26/02/2022 | TECH VISION | 2.62 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Supply & installation of LED board at PH No.-1 of Biraldham Nagar & Jagadishpur water supply scheme under SMD, PHE Dte. |  |  | ORD/001181/2023-2024 | 1O69/SMSD | 17/08/2023 | 27/08/2023 | DITHI ENTERPRISE | 0.78 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1574/SWD-I | 16/10/2022 | 16/10/2022 | Resource Division | 5.22 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 19.84 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/00002/2023-2024 | BP-2023-24-37 | 18/05/2023 | 18/05/2023 | WBSEDCL | 6.02 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at BIRALDHAM NAGAR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 848) | AE BSD | JE-1 | ORD/000250/2022-2023 | 1738/SWD-I | 03/11/2022 | 01/02/2023 | SUJATA CONSTRUCTION | 149.78 | 0 | 0 | 90
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Balance miscellaneous work for Ground water based BIRALDHAM NAGAR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12213) |  |  | ORD/000908/2023-2024 | 1207/SWD-I | 11/03/2024 | 25/04/2024 | S.S. CONSULTANCY & CONSTRUCTION | 26.19 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for BIRALDHAM NAGAR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000146/2022-2023 | 1377/SWD-I | 20/09/2022 | 20/10/2022 | CAPITAL CONSTRUCTION | 40.13 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Biraldham Nagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000471/2022-2023 | 3942/SMD | 30/12/2022 | 30/03/2023 | COOLING CARE CENTER | 9.69 | 0 | 0 | 50
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRALDHAM NAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distri | SM/12213 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House no-1 of BIRALDHAM NAGAR W/S Scheme under SMD, PHE Dte. (Block- Baruipur) |  |  | ORD/002567/2023-2024 | 870/SMSD | 11/07/2023 | 26/07/2023 | COOLING CARE CENTER | 0.99 | 0 | 0 | 100
Total | [13 empty] | 276.58 | 0 | 0