## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I |  | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 30/01/2023 | M/S. SREEJIT ENTERPRISE | 19 | 5.04 | 26.53 | 98
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Additional work for sinking of Rig bored 02 (Two) nos. 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Birlapur (CT) PWSS of Budge Budge-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12214] | AE SWSD-I |  | ORD/000697/2022-2023 | 3500/SWD-I | 16/03/2023 | 31/03/2023 | PADMA ENGINEERING CO. | 6.1 | 6.1 | 100 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Birlapur (CT) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-I] | Assistant Engineer -II | Junior Engineer | ORD/000517/2022-2023 | 376/SMD | 15/02/2023 | 16/05/2023 | M/S. S.S. ENTERPRISE | 25.69 | 23.53 | 91.61 | 80
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Piped Water Supply Scheme at Mayapur Village (JL. - 46) (Sansad III & IV) of Budge Budge - I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. (Route surveying of 40KM) | AE SWSD-I |  | ORD/000194/2022-2023 | 714/SWD-I | 24/06/2022 | 21/12/2022 | CHAYANIKA ENGINEERING CONSULTANCY | 2.9 | 2.53 | 87.5 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia & 300 mtr. deep tube-well by rotary method for water supply at Birlapur (CT) Piped Water Supply Scheme of Budge Budge-I Block under South 24-Parganas W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000299/2022-2023 | 1885/SWD-I | 16/11/2022 | 16/12/2022 | PADMA ENGINEERING CO. | 40.15 | 34.47 | 85.84 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Construction of 02nos. Pump House (Size 4.80mX3.66m) at tubewell site zone- I & II of Birlapur (CT) PWSS of Budge Budge-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12214) | AE SWSD-I |  | ORD/000430/2022-2023 | 2579/SWD-I | 10/01/2023 | 11/03/2023 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 13.69 | 13.02 | 95.12 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Interconnection of Tubewell Sites in Mayapur GP "Ground water based BIRLAPUR (CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas". (TSM/013487) | AE SWSD-I | JE-1 | ORD/000400/2023-2024 | 1909/SWD-I | 21/08/2023 | 05/10/2023 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 7.69 | 7.66 | 99.67 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/00371/2023-2024 | BP-2023-24-26 | 17/05/2023 | 17/05/2023 | WBSEDCL | 7.08 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Bill for electricity payment for security deposit for New Service Connection under SMD, PHE Dte. |  |  | BILL/01302/2022-2023 | BP-2022-23-440 | 10/03/2023 | 10/03/2023 | WBSEDCL | 1.53 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Construction of 2 (Two) nos. boundary walls with allied works for Birlapur CT pipe water supply scheme to accommodate FHTC in Budge Budge-I block under South 24- Parganas. W/S Division-I, PHE Dte. South 24-Pargans District for Augmentation of surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns District. (SM/12214) |  |  | ORD/000366/2024-2025 | 3506/SWD-I | 07/08/2024 | 21/09/2024 | MS KRISHNA MONDAL | 36.9 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Supply, delivery and installation of LED Board and other allied works at P.H. No. - 1 under Birlapur CT Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Budge Budge - I)(SM/12214) | Assistant Engineer -II | Junior Engineer | ORD/002371/2023-2024 | 158-AE-II-SMD | 09/02/2024 | 24/02/2024 | M/S.UTTAM KUMAR CHATTERJEE | 0.75 | 0.75 | 100 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Laying of additional pipeline for Birlapur (CT) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-I Block under South 24-Pgns. Water Supply Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in Arsenic Affected Areas of South 24-Pgns. Dist. (SM/12214) | AE SWSD-I | JE-1 | ORD/000776/2023-2024 | 804/SWD-I | 16/02/2024 | 01/04/2024 | STAR ENTERPRISE | 43.78 | 43.76 | 99.96 | 60
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Construction of Blower room (Size 3.60mX3.00m) Birlapur Piped Water Supply Scheme for Zone-I & Zone-II of Budge Budge-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas. (SM/12214) | AE SWSD-I | JE-1 | ORD/000834/2023-2024 | 1096/SWD-I | 05/03/2024 | 19/04/2024 | SANJAY MIDDEY | 7.06 | 3.39 | 48.04 | 100
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Repair of RIDF Road at Chakatala near Birlapur with allied works under Ground Water Based BIRLAPUR(CT) Piped Water Supply Scheme of South 24 Pargana W/S Supply Division- I, P.H.E Dte. (TSM/013487) | AE SWSD-I | JE-1 | ORD/000837/2023-2024 | 1151/SWD-I | 07/03/2024 | 21/04/2024 | PROJECT AND MAINTENANCE | 16.89 | 16.87 | 99.86 | 100
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Restoration of road and providing pipe supporting structures near Mayapur GP Kabarsthan for BIRLAPUR (CT) piped water supply scheme to accommodate FHTC in Budge Budge -I block under South 24 Parganas W/S Division-I, South 24-Pgns District for Augmentation of Surface Based Water Supply Scheme in the affected areas of South 24-Pgns (SM/12214) | AE SWSD-I | JE-1 | ORD/000382/2024-2025 | 3573/SWD-I | 12/08/2024 | 26/09/2024 | MS POUSALI ENTERPRISE | 3.09 | 3.09 | 100 | 100
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Laying of distribution pipeline and providing FHTC for BIRLAPUR (CT) PWSS including restoration of roads under South 24-Pgns W/S Division-I, P.H.E. Dte., District South 24 Parganas. [No. of FHTC = 2032] | AE SWSD-I | JE-1 | ORD/000510/2022-2023 | 2940/SWD-I | 16/02/2023 | 17/04/2023 | M/S. S.S. ENTERPRISE | 208.47 | 180.05 | 86.37 | 60
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Supply, installation, trail run and commissioning of Pressure Transmitter and display arrangement in connection to Piped water supply scheme for Birlapur CT under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. [SM/12214] |  |  | ORD/001121/2024-2025 | 115/SWD-I | 10/01/2025 | 17/01/2025 | B.S. RUBBER INDUSTRIES | 0.53 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Fitting of Air Valves and Pressure Gauges to different points of Rising Main towards Mayapur Gp near Birlapur (CT) under Birlapur (CT) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-I Block under South 24-Pgns W/S Divn.-I, South 24pgns Dist. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas. (SM/12214) | AE SWSD-I | JE-1 | ORD/001130/2024-2025 | 193/SWD-I | 17/01/2025 | 16/02/2025 | SRIJON ENTERPRISE | 21.72 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Laying of backwash pipe line from newly installed IEP to nearby canal at Birlapur under Birlapur (CT) PWSS to accommodate FHTC in Budge Budge-I block under South 24 Pgns. W/S Division-I, for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12214) |  |  | ORD/000018/2025-2026 | 970/SWD-I | 09/04/2025 | 24/05/2025 | MONDAL PRECISION PVT. LTD. | 20.63 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BIRLAPUR(CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of Sou | SM/12214 | Augmentation | Engagement of expertise to improve the performance and functionality at the end of consumers (FHTC) of the water supply system using Hydraulic Isolation Structures near Birlapur (CT) under South 24-Parganas Water Supply Division-I, PHE Dte. (SM/12214) | AE SWSD-I | JE-1 | ORD/000070/2025-2026 | 1509/SWD-I | 03/06/2025 | 18/07/2025 | AJIVAM WATER PRIVATE LIMITED | 10 | 0 | 0 | 100
Total | [13 empty] | 493.65 | 340.27 | 68.93