## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for DANGA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I |  | ORD/000262/2022-2023 | 1774/SWD-I | 07/11/2022 | 07/12/2022 | TAPAS KUMAR GIRI | 30.07 | 13.69 | 45.54 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Danga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000295/2022-2023 | 444/SMD | 17/02/2023 | 18/05/2023 | A.G.ENTERPRISE | 25.68 | 11.63 | 45.28 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DANGA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12230] | AE HQ-I | JE-3 | ORD/000130/2023-2024 | 618/SWD-I | 17/05/2023 | 01/06/2023 | TAPAS KUMAR GIRI | 3.14 | 1.6 | 50.96 | 5
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 15.6 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000251/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 12.26 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01101/2023-2024 | BP-2023-24-151 | 24/07/2023 | 24/07/2023 | WBSEDCL | 1.3 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12230) |  |  | ORD/000764/2024-2025 | 4685/SWD-I | 18/11/2024 | 02/01/2025 | ARASTA ENGINEERING & CO | 10.18 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Danga W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002208/2023-2024 | 1316/SMSD | 06/10/2023 | 21/10/2023 | A.G.ENTERPRISE | 0.99 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Repairing and renovation of Pump House, Chlorine Room, Construction of Pathway,Drain, Development of land & others allied works at HW Site of "DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12230). | Assistant engineer (contractual) | JE-3 | ORD/000235/2024-2025 | 2655/SWD-I | 07/06/2024 | 22/07/2024 | M/S PIONEER CONSTRUCTION | 22.49 | 18.31 | 81.41 | 70
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1991] | AE HQ-I,AE HQ-II | JE RWS, Sonarpur Block | ORD/000500/2022-2023 | 2882/SWD-I | 13/02/2023 | 29/05/2026 | M/S PIONEER CONSTRUCTION | 418.22 | 211.19 | 50.5 | 50
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of DANGA Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/12230] | Assistant engineer (contractual) | JE-3 | ORD/001100/2024-2025 | 76/SWD-I | 07/01/2025 | 06/02/2025 | B.K.ENTERPRISE | 15.68 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based DANGA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12230 | Augmentation | Supply & Fixing Kiosk Box including allied works at Pump House no-1 of Danga W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002408/2023-2024 | 1312/SMSD | 04/10/2023 | 19/10/2023 | A.G.ENTERPRISE | 0.52 | 0 | 0 | 100
Total | [13 empty] | 556.14 | 256.42 | 46.11