## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Preparation and submission of Detailed Project Report of UTTAR BHAG Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000208/2021-2022 | 1948/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 26.57 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at UTTAR BHAG of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1761] | AE BSD | JE RWS,JE-1 | ORD/000113/2023-2024 | 525/SWD-I | 11/05/2023 | 30/06/2025 | JAL PRAVAHIKA PVT. LTD. | 527.08 | 0 | 0 | 80
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for UTTAR BHAG Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12231] |  |  | ORD/000573/2024-2025 | 4272/SWD-I | 01/10/2024 | 31/10/2024 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Head works site for UTTAR BHAG PWSS to accommodate FHTC in BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/12231] | AE BSD | JE-1 | ORD/000901/2023-2024 | 1328/SWD-I | 15/03/2024 | 30/03/2024 | ARUP ENTERPRISE | 15.73 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00128/2024-2025 | BP-2024-25-40 | 24/04/2024 | 24/04/2024 | WBSEDCL | 5.05 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Charges for new service connection at pump house no-2 of Uttarbhar water supply scheme (Baruipur Block). |  |  | BILL/01726/2024-2025 | BP-2024-25-413 | 30/09/2024 | 30/09/2024 | WBSEDCL | 14.69 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Uttarbhag water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000474/2022-2023 | 3945/SMD | 30/12/2022 | 01/08/2025 | M.S.C ENTERPRISE | 25.93 | 0 | 0 | 40
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Construction of boundary wall including development of land and other allied works for Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/12231) | AE BSD | JE RWS | ORD/000856/2023-2024 | 1248/SWD-I | 13/03/2024 | 19/10/2025 | ARNAB ENTERPRISE | 33.68 | 0 | 0 | 50
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at PH-2 of Uttarbhag W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12231) | Assistant Engineer | Junior Engineer | ORD/002056/2024-2025 | 395/SMSD | 19/03/2025 | 03/04/2025 | M.S.C ENTERPRISE | 0.97 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12231 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Uttarbhag W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12231) |  |  | ORD/002054/2024-2025 | 393/SMSD | 19/03/2025 | 03/04/2025 | M.S.C ENTERPRISE | 0.59 | 0 | 0 | 0
Total | [13 empty] | 668.75 | 0 | 0