## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for JULPIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014900] | AE SWSD-II | JE1 | ORD/000634/2022-2023 | 3278/SWD-I | 03/03/2023 | 18/03/2023 | MOMINUL BISWAS | 1.57 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Preparation and submission of Detailed Project Report of "JULPIA Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district | AE SWSD-II |  | ORD/000420/2022-2023 | 467/SWD-I C | 24/05/2022 | 08/06/2022 | CHAYANIKA ENGINEERING CONSULTANCY | 2.62 | 2.62 | 99.88 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of JULPIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12234) | AE SWSD-II | JE1 | ORD/000434/2022-2023 | 2578/SWD-I | 10/01/2023 | 11/03/2023 | BAKSHI ENTERPRISE | 6.05 | 5.67 | 93.84 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 37.13 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Restoration of damages due to laying of water supply line of PHE Directorate near chainage 10.00 kmp of Amtala - Baruipur Road in the district of South 24 pgs under South 24 pgs. Division, PWD during the year 2022-2023 (Estimated cost Rs.53,10,997/- x 50% = 2655499/-) |  |  | BILL/01314/2023-2024 | BP-2023-24-456 | 03/11/2023 | 03/11/2023 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 26.55 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Payment of Quotation for new service connection at Julpia PWSS, PH No. - I (Dag No. - 152) Application No. - 1007646826 Reference ID - 106555248 |  |  | BILL/00151/2024-2025 | BP-2024-25-47 | 09/05/2024 | 09/05/2024 | WBSEDCL | 5.28 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Payment for final 50% amount of the estimate value after completion of restoration work near chainage 10 km on Amtala Baruipur road as per minutes of the meeting taken by HMIC, PHED with SE's on 12/09/2022 whose total estimate value Rs.53,10,997/-, Less advance 50% payment Rs.26,55,499/-, So. Payment to be made Rs.26,55,498/- |  |  | BILL/00063/2024-2025 | BP-2024-25-52 | 09/05/2024 | 09/05/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 26.55 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based JULPIA Pipe Water Supply Scheme for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs. District. [No. of FHTC=901 nos.] | AE SWSD-II | JE1 | ORD/000421/2022-2023 | 2566/SWD-I | 10/01/2023 | 10/04/2023 | RELIABLE CONSTRUCTIONS | 163.03 | 54.77 | 33.6 | 60
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Julpia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000509/2022-2023 | 348/SMD | 09/02/2023 | 01/07/2025 | AHALYA ENGINEERING WORKS | 22.78 | 7.8 | 34.24 | 50
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 19/03/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Construction of boundary wall, approach road, laying of additional pipeline and other allied works for JULPIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/12234] | AE SWSD-II | JE1 | ORD/000667/2024-2025 | 4414/SWD-I | 24/10/2024 | 20/10/2025 | BAKSHI ENTERPRISE | 58.69 | 0 | 0 | 12
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Land development at JULPIA Piped Water Supply Scheme for 1st Tubewell site in the Arsenic Affected Areas of South 24 Parganas District in Bishnupur-I Block under South 24-Pgns. W/S Sub Division-II, PHE Dte. (SM/12234) | AE SWSD-II | JE1 | ORD/000838/2023-2024 | 1255/SWD-I | 13/03/2024 | 28/03/2024 | HASIBA ENTERPRISE | 2.65 | 0 | 0 | 95
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Supply & Delivery of the additional materials for PH No.-1 of Julpia Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/12234] | Assistant Engineer -II | Junior Engineer | ORD/002351/2024-2025 | 1312-AE-II-SMD | 29/10/2024 | 13/11/2024 | AHALYA ENGINEERING WORKS | 0.26 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED JULPIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN BISHNUPUR-I BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12234 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for JULPIA Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12234] | AE SWSD-II | JE1 | ORD/000694/2024-2025 | 4489/SWD-I | 30/10/2024 | 30/03/2025 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0 | 98
Total | [13 empty] | 474.36 | 70.86 | 14.94