## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Preparation and submission of Detailed Project Report of MAJERHAT Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000169/2021-2022 | 1914/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.62 | 2.62 | 100 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 108.14 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01721/2023-2024 | BP-2023-24-200 | 09/08/2023 | 09/08/2023 | WBSEDCL | 4.73 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at MAJERHAT of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 2233) | AE BSD | JE RWS,JE-2 | ORD/000202/2022-2023 | 1558/SWD-I | 13/10/2022 | 10/02/2023 | K P CONSTRUCTION | 358.83 | 202.91 | 56.55 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Balance work of Laying distribution system for MAJHERHAT PWSS to accommodate FHTC in Baruipur Block under South 24 Pgns Water Supply Division-I, PHE. Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Paraganas District (TSM/012625) | AE BSD | JE RWS,JE-2 | ORD/000043/2023-2024 | 181/SWD-I | 18/04/2023 | 17/07/2023 | K P CONSTRUCTION | 31.15 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Sinking of 03 (three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for MAJERHAT PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD | JE-2 | ORD/000115/2022-2023 | 1276/SWD-I | 13/09/2022 | 13/10/2022 | M/S S R ENTERPRISE | 60.19 | 55.18 | 91.68 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Additional work for Sinking of 03 (Three) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for MAJHERHAT PWSS of BARUIPUR Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/012625] | AE BSD | JE-2 | ORD/000782/2023-2024 | 810/SWD-I | 16/02/2024 | 17/03/2024 | M/S S.R ENTERPRISE | 6.6 | 6.34 | 95.97 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Majherhat W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002713/2023-2024 | 1406/SMMSD | 17/11/2023 | 02/12/2023 | WEST BENGAL ENGINEERING CO. | 0.58 | 0.58 | 100 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Majherhat W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002714/2023-2024 | 1407/SMSD | 17/11/2023 | 02/12/2023 | WEST BENGAL ENGINEERING CO. | 0.9 | 0.9 | 99.81 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Majherhat W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002715/2023-2024 | 1408/SMSD | 17/11/2023 | 02/12/2023 | WEST BENGAL ENGINEERING CO. | 0.9 | 0.9 | 99.61 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05121/2023-2024 | BP-2023-24-579 | 12/03/2024 | 12/03/2024 | WBSEDCL | 3.8 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Construction of 03 (Three) nos. chlorination room at MAJERHAT of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012625] | AE BSD | JE RWS | ORD/000124/2022-2023 | 1292/SWD-I | 14/09/2022 | 02/05/2025 | SWASTIK CONSTRUCTION | 16.4 | 8.34 | 50.85 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Majherhar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000473/2022-2023 | 3944/SMD | 30/12/2022 | 01/04/2025 | WEST BENGAL ENGINEERING CO. | 38.89 | 35.46 | 91.18 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Majherhat W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/12237) | Assistant Engineer | Junior Engineer | ORD/000279/2024-2025 | 644/SMSD | 29/05/2024 | 13/06/2024 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based MAJERHAT piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12237 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-3 of of Majherhat W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12237) | Assistant Engineer | Junior Engineer | ORD/000280/2024-2025 | 676/SMSD | 04/06/2024 | 19/06/2024 | WEST BENGAL ENGINEERING CO. | 0.29 | 0 | 0 | 100
Total | [13 empty] | 634.94 | 313.23 | 49.33