## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Preparation and submission of Detailed Project Report of PANCH GACHHIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000405/2021-2022 | 1940/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 2.76 | 2.56 | 92.79 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 24.23 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Construction of boundary walls, platform for FHTC, protection of pipeline, development of land and other allied works for Ground water based PANCH GACHHIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/12240) |  |  | ORD/000333/2024-2025 | 3271/SWD-I | 22/07/2024 | 05/09/2024 | S. ROY AND ASSOCIATES | 66.2 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PANCHGACHIA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/12240] | AE BSD | JE-2 | ORD/000563/2022-2023 | 3060/SWD-I | 21/02/2023 | 23/03/2023 | AKBAR ALI | 31.75 | 30.56 | 96.25 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04686/2023-2024 | BP-2023-24-513 | 12/02/2024 | 12/02/2024 | WBSEDCL | 13.25 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Charges for service connection at Panchagachia-II |  |  | BILL/00487/2024-2025 | BP-2024-25-115 | 14/06/2024 | 14/06/2024 | WBSEDCL | 14.23 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at PANCH GACHIA of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1143] | AE BSD | JE-1 | ORD/000033/2023-2024 | 117/SWD-I | 11/04/2023 | 21/03/2026 | M/S. GOUTAM ROY | 172.9 | 45.01 | 26.03 | 60
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Panch Gachia supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 600/SMD | 27/02/2023 | 01/07/2025 | AHALYA ENGINEERING WORKS | 23.98 | 0 | 0 | 80
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 & 2 of Panch Gachia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12240) | Assistant Engineer | Junior Engineer | ORD/002180/2024-2025 | 441/SMSD | 21/03/2025 | 05/04/2025 | ESENCE ENGINEERING CONCERN | 0.85 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Construction of Pump house cum Chlorine room (Two nos) at PANCH GACHIA piped water supply scheme to accommodate FHTC in BARUIPUR/JOYNAGAR-I BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/12240) | AE BSD | JE-1 | ORD/000657/2024-2025 | 4389/SWD-I | 23/10/2024 | 22/12/2024 | ISHIYA ENTERPRISE | 9.73 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PANCH GHCHIA piped water supply scheme to accommodate FHTC in BARUIPUR, JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Pargan | SM/12240 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-2 of Panch Gachia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12240) | Assistant Engineer | Junior Engineer | ORD/002252/2024-2025 | 443/SMSD | 21/03/2025 | 05/04/2025 | AHALYA ENGINEERING WORKS | 0.52 | 0 | 0 | 100
Total | [13 empty] | 360.4 | 78.13 | 21.68