## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Preparation and submission of Detailed Project Report of KUNDALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000162/2021-2022 | 1924/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.76 | 2.76 | 100 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000269/2023-2024 | 2423/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 64.82 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000306/2023-2024 | 2443/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 54.51 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01104/2023-2024 | BP-2023-24-150 | 24/07/2023 | 24/07/2023 | WBSEDCL | 5.14 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03526/2023-2024 | BP-2023-24-389 | 23/11/2023 | 23/11/2023 | WBSEDCL | 0.14 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kundarali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000462/2022-2023 | 3939/SMD | 30/12/2022 | 30/03/2023 | A.S.ENTERPRISE | 25.96 | 11.88 | 45.77 | 53
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KUNDARALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/012662] | AE BSD | JE-1 | ORD/000188/2022-2023 | 1481/SWD-I | 27/09/2022 | 27/10/2022 | PADMA ENGINEERING CO. | 40.17 | 17.92 | 44.62 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kundarali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/012662] | AE BSD | JE-1 | ORD/000798/2022-2023 | 3671/SWD-I | 29/03/2023 | 13/04/2023 | PADMA ENGINEERING CO. | 4.41 | 2.2 | 50 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH-1 of Kundarali W/S Scheme under SMD PHE Dte. (Block-Baruipur) |  |  | ORD/001649/2023-2024 | 1308/SMSD | 03/10/2023 | 18/10/2023 | A.S.ENTERPRISE | 0.92 | 0.92 | 100 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Construction of 02 (Two) nos. chlorination room at KUNDARALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012662] | AE BSD | JE-2 | ORD/000116/2022-2023 | 1284/SWD-I | 14/09/2022 | 29/08/2025 | MA DURGA ENTERPRISE | 10.93 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KUNDARALI of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1571) | AE BSD | JE RWS,JE-2 | ORD/000221/2022-2023 | 1639/SWD-I | 20/10/2022 | 31/03/2026 | PROJECT AND MAINTENANCE | 333.83 | 220.29 | 65.99 | 98
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for ''Proposed Ground Water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.'' (SM/12266) | AE BSD | JE RWS | ORD/000367/2024-2025 | 3507/SWD-I | 07/08/2024 | 15/12/2025 | PROJECT AND MAINTENANCE | 96.98 | 14.73 | 15.19 | 30
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at PH-2 of Kundarali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12266) | Assistant Engineer | Junior Engineer | ORD/001760/2024-2025 | 414/SMSD | 20/03/2025 | 04/04/2025 | A.S.ENTERPRISE | 0.97 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-2 of Kundarali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12266) | Assistant Engineer | Junior Engineer | ORD/001761/2024-2025 | 413/SMSD | 20/03/2025 | 04/04/2025 | A.S.ENTERPRISE | 0.29 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. | SM/12266 | Augmentation | Sinking of additional 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 3rd Tubewell Site for KUNDARALI PWSS to accommodate FHTC in Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte. for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Pgns. District. [SM/12266] |  |  | ORD/000128/2025-2026 | 2026/SWD-I | 04/08/2025 | 03/09/2025 | DEV & COMPANY | 15.9 | 0 | 0 | 0
Total | [13 empty] | 657.72 | 270.71 | 41.16