## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Preparation and submission of Detailed Project Report of HARIMUL Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000218/2021-2022 | 1935/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for HARIMUL PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011095] | AE BSD |  | ORD/000212/2022-2023 | 1584/SWD-I | 17/10/2022 | 16/11/2022 | SAIKAT ENTERPRISE | 28.4 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Harimul water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000449/2022-2023 | 3929/SMD | 30/12/2022 | 30/03/2023 | JAGANNATH ENTERPRISE | 22.34 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for HARIMUL PWSS of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/011095] | AE BSD |  | ORD/000449/2023-2024 | 2104/SWD-I | 30/08/2023 | 14/09/2023 | SAIKAT ENTERPRISE | 3.14 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Material Requisition To Resource Division |  |  | RTOR000301/2023-2024 | 2439/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 62.89 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at HARIMUL Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC= 1433) | AE BSD | JE-1 | ORD/000029/2023-2024 | 110/SWD-I | 11/04/2023 | 05/02/2024 | CE INFRASTRUCTURE | 433.03 | 0 | 0 | 70
7 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Construction of boundary walls including development of land and other allied works for Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12635) |  |  | ORD/000409/2024-2025 | 3706/SWD-I | 23/08/2024 | 07/10/2024 | C.E. INFRASTRUCTURE | 43.76 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Charges for new service connection at pump house no-2 of Harimul water supply scheme (Baruipur Block) |  |  | BILL/01680/2024-2025 | BP-2024-25-398 | 27/09/2024 | 27/09/2024 | WBSEDCL | 4.93 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Baruipur | Alipore Division | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) |  |  | BILL/01670/2024-2025 | BP-2024-25-777 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04709/2023-2024 | BP-2023-24-520 | 17/02/2024 | 17/02/2024 | WBSEDCL | 5.39 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Construction of 02 (Two) nos. chlorination room at Harimul at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE-1 | ORD/000352/2022-2023 | 2200/SWD-I | 13/12/2022 | 31/05/2025 | BANGA NIRMAN | 11.51 | 0 | 0 | 50
12 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for HARIMUL Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12635] |  |  | ORD/001156/2024-2025 | 374/SWD-I | 04/02/2025 | 06/03/2025 | G.S. CONSTRUCTION | 15.9 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Harimul W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12635) | Assistant Engineer | Junior Engineer | ORD/000183/2025-2026 | 504/SMSD | 04/04/2025 | 19/04/2025 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Harimul W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12635) | Assistant Engineer | Junior Engineer | ORD/000181/2025-2026 | 707/SMSD | 15/05/2025 | 30/05/2025 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12635 | New | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Harimul W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12635) | Assistant Engineer | Junior Engineer | ORD/000184/2025-2026 | 503/SMSD | 04/04/2025 | 19/04/2025 | JAGANNATH ENTERPRISE | 0.58 | 0 | 0 | 0
Total | [13 empty] | 636.94 | 0 | 0