## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Construction of 02 (Two) nos. chlorination rooms at Jelerhat at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD |  | ORD/000365/2022-2023 | 2208/SWD-I | 13/12/2022 | 11/02/2023 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 11.52 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JELERHAT PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011011] | AE BSD |  | ORD/000216/2022-2023 | 1593/SWD-I | 17/10/2022 | 16/11/2022 | SAIKAT ENTERPRISE | 28.4 | 4.04 | 14.21 | 10
3 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jelerhat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000451/2022-2023 | 3931/SMD | 30/12/2022 | 30/03/2023 | JAGANNATH ENTERPRISE | 22.37 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Preparation and submission of Detailed Project Report of JELERHAT Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000220/2021-2022 | 1936/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.69 | 97.49 | 0
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Jelerhat PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011011] | AE BSD |  | ORD/000724/2022-2023 | 3573/SWD-I | 22/03/2023 | 06/04/2023 | SAIKAT ENTERPRISE | 3.14 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JELERHAT Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1675) | AE BSD | JE RWS Baruipur Block | ORD/000739/2022-2023 | 3592/SWD-I | 23/03/2023 | 17/01/2024 | THE UNICON ENGINEERS | 422.87 | 259.26 | 61.31 | 70
7 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Material Requisition To Resource Division |  |  | RTOR000333/2023-2024 | 266/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 10.32 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Baruipur | Alipore Division | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) |  |  | BILL/01674/2024-2025 | BP-2024-25-779 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Charges for service connection at Pump house no-I of Jelerhat.(Baruipur Block) |  |  | BILL/00403/2024-2025 | BP-2024-25-98 | 10/06/2024 | 10/06/2024 | WBSEDCL | 5.08 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12636 | New | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for JELERHAT Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12636] |  |  | ORD/001155/2024-2025 | 373/SWD-I | 04/02/2025 | 06/03/2025 | RAJKUMAR MONDAL | 15.9 | 0 | 0 | 0
Total | [13 empty] | 522.89 | 265.99 | 50.87