## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Preparation and submission of Detailed Project Report of "GOKARNEE Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000386/2022-2023 | 406/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 26.3 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of GOKARNI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1585] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000487/2022-2023 | 2792/SWD-I | 01/02/2023 | 28/11/2023 | MONDAL PRECISION PVT. LTD. | 463.13 | 0 | 0 | 25
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of Boundary wall at HW site for GOKARNI PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas.(SM/12771) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000329/2024-2025 | 3267/SWD-I | 22/07/2024 | 05/09/2024 | M/S. SREEJIT ENTERPRISE | 23.82 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of boundary wall & approach Road at 2nd Tube Well site for GOKARNI PWSS to accommodate FHTC in Magrahat-II block under South 24 Parganas W/S division-I, P.H.E. Dte for augmentation of surface water Based Water supply Scheme in the arsenic affected areas of South 24-Pgns district (SM/12771) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000328/2024-2025 | 3265/SWD-I | 22/07/2024 | 20/10/2024 | SANJAY MIDDEY | 12.19 | 0 | 0 | 60
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of Platform for providing FHTC for Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. [No. of FHTC= 1585] (SM/12771) |  |  | ORD/000344/2024-2025 | 3318/SWD-I | 23/07/2024 | 21/09/2024 | MONDAL PRECISION PVT. LTD. | 29.5 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Gokarni PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division | JE RWS, HQ | ORD/000300/2022-2023 | 1878/SWD-I | 16/11/2022 | 16/12/2022 | KUNTAL CHOWDHURY | 30.03 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Gokarni PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014757] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000007/2023-2024 | 29/SWD-I | 05/04/2023 | 20/04/2023 | KUNTAL CHOWDHURY | 3.13 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of Hume Pipe culvert for the approach road of proposed "Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block, South 24 Parganas District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE, Dte. (TSM/014757) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000152/2023-2024 | 721/SWD-I | 29/05/2023 | 28/07/2023 | TOJO ENTERPRISE | 10.17 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Balance work for Construction of Humc Pipe culvert for the approach road of proposcd "Ground water bascd GOKARNI piped watcr supply schcmc to accommodate FHTC tn MAGRAHAT-II block, South 24 Parganas Djstnct for Augmentation of Surfacc Water Based Water Supply Scheme In the Arscmc Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE. Dle (TSM/014757) |  |  | ORD/000794/2023-2024 | 1142/SWD-I | 07/03/2024 | 06/04/2024 | TOJO ENTERPRISE | 2.41 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Quotation for new service connection at P.H. NO.1 of Gokarni w/s scheme . Application no.: 1007730295 . |  |  | BILL/00534/2024-2025 | BP-2024-25-132 | 24/06/2024 | 24/06/2024 | WBSEDCL | 3.95 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Gokarni water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000394/2022-2023 | 3796/SMD | 29/12/2022 | 01/01/2026 | M/S. A.K. BANERJEE | 22.35 | 0 | 0 | 45
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gokorni W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) (SM/12771) | Assistant Engineer | Junior Engineer | ORD/000918/2025-2026 | 640/SMSD | 30/04/2025 | 15/05/2025 | M/S. A.K. BANERJEE | 0.85 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Supply & laying of submersible cable through non metallic pipes for electrical connection of pumping machinery with Pump House no-1 of Gokorni W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) (SM/12771) | Assistant Engineer | Junior Engineer | ORD/000919/2025-2026 | 641/SMSD | 30/04/2025 | 15/05/2025 | M/S. A.K. BANERJEE | 0.82 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement at 2nd Tubewell site of Gokarni PWSS to accommodate FHTC in MOGRAHAT-II Block for augmentation of surface water based WS scheme in the arsenicaffected areas of South 24 Parganas district, South 24 Pgns WS Division-I, P.H.E Dte. (SM/12771) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000663/2024-2025 | 4393/SWD-I | 23/10/2024 | 30/07/2025 | SANJAY MIDDEY | 5.89 | 0 | 0 | 65
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of chlorination room 5.00mx4.00m(One no) at Head work site of GOKARNI PWSS to accommondate FHTC in MOGRAHAT-II Block under South 24 Pngs Divn-I, PHE Dte for augmentation of surface water based WS scheme in the arsenic affected areas of South 24 Parganas District. (SM/12771) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000413/2024-2025 | 3714/SWD-I | 23/08/2024 | 05/04/2025 | CHOUDHURY AND ASSOCIATES | 4.86 | 0 | 0 | 40
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement at GOKARNI Head Work site of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based WS scheme in the arsenicaffected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns WS Division-I, P.H.E Dte. (SM/12771) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000541/2024-2025 | 4098/SWD-I | 20/09/2024 | 28/03/2025 | GLANCE CONSTRUCTION | 5.9 | 0 | 0 | 50
Total | [13 empty] | 648.14 | 0 | 0