## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Preparation and submission of Detailed Project Report of "GOKARNEE Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000386/2022-2023 | 406/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 26.3 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of GOKARNI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1585] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000487/2022-2023 | 2792/SWD-I | 01/02/2023 | 28/11/2023 | MONDAL PRECISION PVT. LTD. | 463.13 | 0 | 0 | 25
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of Boundary wall at HW site for GOKARNI PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas.(SM/12771) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000329/2024-2025 | 3267/SWD-I | 22/07/2024 | 05/09/2024 | M/S. SREEJIT ENTERPRISE | 23.82 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of boundary wall & approach Road at 2nd Tube Well site for GOKARNI PWSS to accommodate FHTC in Magrahat-II block under South 24 Parganas W/S division-I, P.H.E. Dte for augmentation of surface water Based Water supply Scheme in the arsenic affected areas of South 24-Pgns district (SM/12771) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000328/2024-2025 | 3265/SWD-I | 22/07/2024 | 20/10/2024 | SANJAY MIDDEY | 12.19 | 0 | 0 | 60
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of Platform for providing FHTC for Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. [No. of FHTC= 1585] (SM/12771) |  |  | ORD/000344/2024-2025 | 3318/SWD-I | 23/07/2024 | 21/09/2024 | MONDAL PRECISION PVT. LTD. | 29.5 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Gokarni PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division | JE RWS, HQ | ORD/000300/2022-2023 | 1878/SWD-I | 16/11/2022 | 16/12/2022 | KUNTAL CHOWDHURY | 30.03 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Gokarni PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014757] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000007/2023-2024 | 29/SWD-I | 05/04/2023 | 20/04/2023 | KUNTAL CHOWDHURY | 3.13 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Construction of Hume Pipe culvert for the approach road of proposed "Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block, South 24 Parganas District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE, Dte. (TSM/014757) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000152/2023-2024 | 721/SWD-I | 29/05/2023 | 28/07/2023 | TOJO ENTERPRISE | 10.17 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Balance work for Construction of Humc Pipe culvert for the approach road of proposcd "Ground water bascd GOKARNI piped watcr supply schcmc to accommodate FHTC tn MAGRAHAT-II block, South 24 Parganas Djstnct for Augmentation of Surfacc Water Based Water Supply Scheme In the Arscmc Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE. Dle (TSM/014757) |  |  | ORD/000794/2023-2024 | 1142/SWD-I | 07/03/2024 | 06/04/2024 | TOJO ENTERPRISE | 2.41 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Quotation for new service connection at P.H. NO.1 of Gokarni w/s scheme . Application no.: 1007730295 . |  |  | BILL/00534/2024-2025 | BP-2024-25-132 | 24/06/2024 | 24/06/2024 | WBSEDCL | 3.95 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Gokarni water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000394/2022-2023 | 3796/SMD | 29/12/2022 | 01/01/2026 | M/S. A.K. BANERJEE | 22.35 | 0 | 0 | 45
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gokorni W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) (SM/12771) | Assistant Engineer | Junior Engineer | ORD/000918/2025-2026 | 640/SMSD | 30/04/2025 | 15/05/2025 | M/S. A.K. BANERJEE | 0.85 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of S | SM/12771 | Augmentation | Supply & laying of submersible cable through non metallic pipes for electrical connection of pumping machinery with Pump House no-1 of Gokorni W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) (SM/12771) | Assistant Engineer | Junior Engineer | ORD/000919/2025-2026 | 641/SMSD | 30/04/2025 | 15/05/2025 | M/S. A.K. BANERJEE | 0.82 | 0 | 0 | 0
Total | [13 empty] | 631.48 | 0 | 0