## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Heria PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. |  |  | ORD/000296/2022-2023 | 1876/SWD-I | 16/11/2022 | 16/12/2022 | DIPALI CONSTRUCTION | 30.03 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Heria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000395/2022-2023 | 3797/SMD | 29/12/2022 | 29/03/2023 | A.K.SIKDAR | 22.21 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Preparation and submission of Detailed Project Report of "HERIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000390/2022-2023 | 409/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.76 | 2.64 | 95.76 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Construction of 200 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of HERIA of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1561] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000529/2022-2023 | 2949/SWD-I | 16/02/2023 | 13/12/2023 | M/S PRADIP KUMAR PAL (EMAIL ID- PRADIPKUMARPAL.CO@GMAIL.COM) | 378.82 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Heria PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014760] | AE RWS, Alipore Division |  | ORD/000015/2023-2024 | 39/SWD-I | 06/04/2023 | 21/04/2023 | DIPALI CONSTRUCTION | 3.13 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 26.16 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for HERIA Piped Water Supply Scheme of MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. (SM/12772) |  |  | ORD/000788/2023-2024 | 1071/SWD-I | 04/03/2024 | 03/04/2024 | M/S ARINDAM MONDAL | 29.88 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for HERIA Piped Water Supply Scheme of MOGRAHAT-II Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12772] |  |  | ORD/000845/2023-2024 | 1251/SWD-I | 13/03/2024 | 12/04/2024 | M/S ARINDAM MANDAL | 3.12 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Construction of Boundary wall (length = 57.60m), Development of land, Construction of Service Road (length = 15.00m) and Pump House at 2nd Tubewell site for HERIA PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Divn.-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12772) |  |  | ORD/001160/2024-2025 | 401/SWD-I | 06/02/2025 | 07/04/2025 | BHANDARY CONSTRUCTION | 15.38 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HERIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sou | SM/12772 | Augmentation | Development of Land, Construction of Boundary wall (length = 144.00m), Approach Road (length = 30.00m) and Construction of Pump House (5.40 Mtr. X 3.60 Mtr.) with water supply & sanitary arrangementat OHR site (1st Tube well Site) for HERIA PWSS to accommodate FHTC in MAGRAHAT-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12772) |  |  | ORD/000009/2025-2026 | 933/SWD-I | 07/04/2025 | 06/06/2025 | SUBHO CONSTRUCTION | 32.33 | 0 | 0 | 0
Total | [13 empty] | 543.82 | 2.64 | 0.49