## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Preparation and submission of Detailed Project Report of "CHAK PARANKANTAKHALI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000391/2022-2023 | 410/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ChakParankanta Khali PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014899] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000734/2022-2023 | 3585/SWD-I | 22/03/2023 | 06/04/2023 | TAPAS KUMAR GIRI | 3.14 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Chak Parankanta Khali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 3802/SMD | 29/12/2022 | 29/03/2023 | M/S.P.P.ELECTRICALS | 22.35 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 23.83 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of CHAK PARANKANTA KHALI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1785] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000486/2022-2023 | 2790/SWD-I | 01/02/2023 | 28/11/2023 | M/S GHOSH AND CO. | 435.23 | 0 | 0 | 30
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Construction of chlorination room 5.00mx4.00m(One no) at Head work site of CHAK PARANKANTA KHALI PWSS to accommondate FHTC in MOGRAHAT-II Block under South 24 Pgns Divn-I, (SM/12801) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000440/2024-2025 | 3885/SWD-I | 03/09/2024 | 03/10/2024 | AHANA ENTERPRISE | 4.87 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Construction of (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement at CHAK PARANKANTA KHALI Head Work site of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based WS scheme in the arsenicaffected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns WS Division-I, P.H.E Dte. (SM/12801) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000542/2024-2025 | 4099/SWD-I | 20/09/2024 | 19/11/2024 | LASKAR CONSTRUCTION | 5.89 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Construction of Boundary Wall and Approach Road With Drum Sheet walling & Earth filling for CHAK PARANKANTA KHALI PWSS to accommodate FHTC within Mograhat-II Block under South 24 pgs water supply Division-I, PHE Dte. Dist S24 Pgs. (SM/12801) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000295/2024-2025 | 3135/SWD-I | 10/07/2024 | 17/02/2025 | LASKAR CONSTRUCTION | 38.36 | 0 | 0 | 45
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell by Rotary method for CHAK PARANKATA KHALI Piped Water Supply Scheme to accommodate FHTC in MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12801] | AE RWS, Alipore Division | JE RWS, HQ | ORD/001153/2024-2025 | 371/SWD-I | 04/02/2025 | 02/09/2025 | TITUMIR INTERNATIONAL | 36.84 | 0 | 0 | 50
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED CHAK PARANKANTA KHALI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MEGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12801 | Augmentation | Construction of Boundary wall & land development at 2nd Tubewell site including provision of M.S. gate for CHAK PARANKANTA KHALI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. (SM/12801) [Length - 52.0 mtr. of boundary wall] |  |  | ORD/000087/2025-2026 | 1762/SWD-I | 02/07/2025 | 16/08/2025 | MOTIONMASS TECHNO OPC PVT LTD | 9.61 | 0 | 0 | 0
Total | [13 empty] | 582.94 | 0 | 0