## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Preparation and submission of Detailed Project Report of "KULDIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000395/2022-2023 | 419/SWD-I | 20/05/2022 | 04/06/2022 | CHAYANIKA ENGINEERING CONSULTANCY | 2.9 | 2.6 | 89.71 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Kuldia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000405/2022-2023 | 3803/SMD | 29/12/2022 | 29/03/2023 | PADMA ENGINEERING CO. | 22.36 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kuldia PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014902] | AE RWS, Alipore Division |  | ORD/000017/2023-2024 | 40/SWD-I | 06/04/2023 | 21/04/2023 | MUNNA AGROTECH ENTERPRISE | 3.13 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 18.19 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Development of Land, Construction of Boundary wall (length = 175.00m) & Construction of Approach Road (length = 50.00m) at Head Work Site for Kuldia PWSS to Accommodate FHTC in Mograhat-II Block under South 24 Pngs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12802) |  |  | ORD/000422/2024-2025 | 3750/SWD-I | 28/08/2024 | 12/10/2024 | J. ENTERPRISE | 50.01 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of KULDIA of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1615] (SM/12802) |  |  | ORD/000583/2024-2025 | 4343/SWD-I | 08/10/2024 | 08/10/2025 | I.S ENTERPRISE | 372.46 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Kuldia PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000303/2022-2023 | 1880-SWD-I | 16/11/2022 | 30/05/2024 | MUNNA AGROTECH ENTERPRISE | 30.02 | 5.89 | 19.62 | 38
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Construction of 02 (Two) Pump Houses, one at TW-2 site and other at OHR site of KULDIA PWSS to accommodate FHTC in MAGRAHAT-II block South 24-Pgns District under South 24-Pgns W/S Division-I, P.H.E. Dte. (SM/12802) |  |  | ORD/000083/2025-2026 | 1758/SWD-I | 02/07/2025 | 31/08/2025 | KALAM ENTERPRISE | 12.03 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROPOSED GROUND WATER BASED KULDIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MAGRAHAT-II BLOCK UNDER SOUTH 24 PARGANAS DISTRICT. | SM/12802 | Augmentation | Sinking of rig ground bored 250 mm x 150 mm dia & 360 mtr. deep tube-well having 66 mtr housing pipe by Rotary method at Head work site for Kuldia PWSS to accommodate FHTC in Mograhat-II Block under South 24-Parganas W/S Division-I, South 24-Pgns District for Augmentation of surface water baswd water supply scheme in the Arsenic Affected Areas of South 24-Pgns District. (SM/12802) | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000347/2024-2025 | 3362/SWD-I | 26/07/2024 | 08/03/2025 | PADMA ENGINEERING CO. | 19.11 | 0 | 0 | 100
Total | [13 empty] | 530.21 | 8.49 | 1.6