## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Preparation and submission of Detailed Project Report of "NAINAN Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000392/2022-2023 | 404/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.9 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Nainan PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. (2nd Call) | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000357/2022-2023 | 2276/SWD-I | 15/12/2022 | 14/01/2023 | SAHI MASUM | 29.69 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Nainan PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014759] | AE RWS, Alipore Division |  | ORD/000735/2022-2023 | 3586/SWD-I | 22/03/2023 | 06/04/2023 | SAHI MASUM | 3.14 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Nainan water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000396/2022-2023 | 3798/SMD | 29/12/2022 | 29/03/2023 | ABHISEK ENGINEERING CONCERN | 22.36 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 28.49 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of NAINAN of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1684] | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000546/2022-2023 | 3028/SWD-I | 20/02/2023 | 12/03/2025 | SRI RAM CONSTRUCTION | 382.88 | 0 | 0 | 70
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Development of Land, Construction of Boundary wall (length = 175.00m) & Construction of Approach Road (length = 50.00m) at Head Work Site for NAINAN PWSS to Accommodate FHTC in Mograhat-II Block under South 24 Pngs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12803) | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000421/2024-2025 | 3749/SWD-I | 28/08/2024 | 07/10/2025 | SRI RAM CONSTRUCTION | 43.25 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NAINAN piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of So | SM/12803 | Augmentation | Construction of 02 (Two) Pump Houses, one at TW-2 site and other at OHR site of NAINAN PWSS to accommodate FHTC in MAGRAHAT-II block South 24-Pgns District under South 24-Pgns W/S Division-I, PHE Dte. for augmentation of surface water bassed W/S scheme in the arsenic affected areas of South 24 Parganas District. (SM/12803) | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000084/2025-2026 | 1759/SWD-I | 02/07/2025 | 31/08/2025 | SRI RAM CONSTRUCTION | 12.02 | 0 | 0 | 0
Total | [13 empty] | 524.73 | 0 | 0