## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Ramchandra Nagar (Zone-I) PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. |  |  | ORD/000295/2022-2023 | 1882/SWD-I | 16/11/2022 | 16/12/2022 | BARI ENTERPRISE | 30.03 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Ramchandranagar (Part-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000397/2022-2023 | 3799/SMD | 29/12/2022 | 29/03/2023 | KARTICK BAL | 22.21 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Preparation and submission of Detailed Project Report of "RAMCHANDRANAGAR (PART-I) Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000393/2022-2023 | 407/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 2.67 | 94.57 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of RAMCHANDRANAGAR (Part-I) of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1672] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000512/2022-2023 | 2942/SWD-I | 16/02/2023 | 31/08/2025 | RELIABLE ENTERPRISE | 420.98 | 30.04 | 7.13 | 15
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Ramchandra Nagar-I PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014752] | AE RWS, Alipore Division |  | ORD/000782/2022-2023 | 3673/SWD-I | 29/03/2023 | 13/04/2023 | BARI ENTERPRISE | 3.13 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 26.75 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Construction of Service Road (length = 550.00m) and Culvert at OHR site for RAMCHANDRANAGAR (Part-I) PWSS within Mograhat-II under South 24-Pgns, W/S Division-I. P.H.E. Dte. for Augmentation of Surface Water based Water Supply Scheme for Arsenic Affected areas of South 24 Parganas District. (SM/12804) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000870/2024-2025 | 4928/SWD-I | 03/12/2024 | 02/01/2025 | S.M. ENTERPRISE (MOGRAHAT) | 79.56 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Construction of Platform for providing FHTC for Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12804) |  |  | ORD/000319/2024-2025 | 3252/SWD-I | 19/07/2024 | 17/09/2024 | RELIABLE ENTERPRISE (MURSHIDABAD) | 31.12 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Construction of Boundary wall (length= 51.00m), Development of land, Construction of Service Road (Length = 15.00m) and pumphouse (4.80 Mtr x 366 Mtr) at 2nd Tubewell site for RAMCHANDRANAGAR (Part-I) PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District South 24-Parganas. (SM/12804) |  |  | ORD/001176/2024-2025 | 502/SWD-I | 18/02/2025 | 19/04/2025 | SAYAN ENTERPRISE | 14.96 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Af | SM/12804 | Augmentation | Development of land, Construction of Boundary wall, Approach Road and Pump house with water supply and sanitary arrangement at Head Work site for RAMCHANDRANAGAR (Part-I) PWSS OHR site of Mograhat-II Block under South 24 Pgs W/S Division -I, P.H.E. Dte. for Augmentation of Surface Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. (SM/12804) |  |  | ORD/001181/2024-2025 | 607/SWD-I | 27/02/2025 | 13/04/2025 | M/S LAKHI CONSTRUCTION | 29.15 | 0 | 0 | 0
Total | [13 empty] | 660.74 | 32.71 | 4.95