## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Preparation and submission of Detailed Project Report of "RAMCHANDRANAGAR (PART-II) Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000394/2022-2023 | 408/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.76 | 2.64 | 95.61 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Ramchandra Nagar (Zone-II) PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000297/2022-2023 | 1883/SWD-I | 16/11/2022 | 16/12/2022 | MERAJUL ALAM | 29.97 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Ramchandra Nagar (II) PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014755] | AE RWS, Alipore Division |  | ORD/000629/2022-2023 | 3256/SWD-I | 02/03/2023 | 17/03/2023 | MERAJUL ALAM | 3.14 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Ramchandranagar (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000399/2022-2023 | 3800/SMD | 29/12/2022 | 29/03/2023 | KUNDU ELECTRICAL ENTERPRISE | 17.48 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2 of Ramchandranagar (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000410/2023-2024 | 2499/SMD | 14/07/2023 | 12/10/2023 | M/S. G.P ENTERPRISE | 21.62 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2 of Ramchandranagar (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000409/2023-2024 | 2498/SMD | 14/06/2023 | 12/09/2023 | M/S. G.P ENTERPRISE | 21.62 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 25.52 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Land development, Construction of Boundary wall (length = 204.00m) & Construction of Service Road (length = 140.00m) at OHR site for RAMCHANDRANAGAR (Part-II) PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas. (SM/12805) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000365/2024-2025 | 3510/SWD-I | 07/08/2024 | 21/09/2024 | PRONICON INDIA | 54.27 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Repairing of Damaged road by Laying of pipe line for Ground water based RAMCHANDRANAGAR (Part-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block under South 24-Pgns, Water Supply Division-I, South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/12805) |  |  | ORD/000674/2024-2025 | 4463/SWD-I | 29/10/2024 | 28/12/2024 | MOTIONMASS TECHNO OPC PVT LTD | 21.67 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of RAMCHANDRANAGAR (Part-II) of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1580] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000490/2022-2023 | 2820/SWD-I | 03/02/2023 | 01/01/2026 | NEW ALIGNMENT | 384.03 | 99.37 | 25.88 | 40
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based RAMCHANDRANAGAR (PART-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic A | SM/12805 | Augmentation | Construction of Boundary wall (length = 51.00m), Service Road (length = 15.00m), Development of Land, Construction of Pump House (4.80 Mtr. X 3.60 Mtr.) at TW-2 site and Pump House (5.40 Mtr. X 3.60 Mtr.) at OHR site for RAMCHANDRANAGAR (Part-II) PWSS to accommodate FHTC in MAGRAHAT-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12805) |  |  | ORD/000010/2025-2026 | 934/SWD-I | 07/04/2025 | 06/06/2025 | SUBHO CONSTRUCTION | 19.99 | 0 | 0 | 0
Total | [13 empty] | 602.05 | 102.01 | 16.94