## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Shyamnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000401/2022-2023 | 3801/SMD | 29/12/2022 | 29/03/2023 | KUNDU ELECTRICAL ENTERPRISE | 22.25 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Preparation and submission of Detailed Project Report of "SHYAMNAGAR Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000385/2022-2023 | 405/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 2.54 | 89.86 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of SHYAMNAGAR of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1642] | AE RWS, Alipore Division | JE RWS, Magrahat-II Block | ORD/000513/2022-2023 | 2943/SWD-I | 16/02/2023 | 31/05/2025 | JAMIRUL CONSTRUCTION | 339.61 | 0 | 0 | 10
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Shyam Nagar PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014761] | AE RWS, Alipore Division |  | ORD/000731/2022-2023 | 3583/SWD-I | 22/03/2023 | 06/04/2023 | TAPAS KUMAR GIRI | 3.14 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 24.48 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Construction of 900mm Dia Double Row Hume Pipe Culvert for SHYAMNAGAR PWSS under Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12806) |  |  | ORD/000662/2024-2025 | 4392/SWD-I | 23/10/2024 | 22/11/2024 | N CONSTRUCTION | 6.18 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Construction of Platform for providing FHTC for Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12806) |  |  | ORD/000324/2024-2025 | 3257/SWD-I | 19/07/2024 | 17/09/2024 | JAMIRUL CONSTRUCTION | 30.56 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas o | SM/12806 | Augmentation | Development of Land, Construction of Boundary Wall (length=175.00m) & Construction of Service Road (length=140.00m) at OHR Site (1st Tubewell Site) for SHYAMNAGAR PWSS within Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based WAter Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12806) |  |  | ORD/000681/2024-2025 | 4476/SWD-I | 30/10/2024 | 28/01/2025 | R.K ENTERPRISE | 55.77 | 0 | 0 | 0
Total | [13 empty] | 484.82 | 2.54 | 0.52