## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Construction of 02 (Two) nos. chlorination rooms at Champahati (Zone-II) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD |  | ORD/000358/2022-2023 | 2201/SWD-I | 13/12/2022 | 11/02/2023 | THE DESIGN IN | 10.72 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Preparation and submission of Detailed Project Report of CHAMPAHATI(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000446/2021-2022 | 1954/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100 | 100
3 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for CHAMPAHATI (ZONE-II) PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/010745] | AE BSD | JE-2 | ORD/000214/2022-2023 | 1586/SWD-I | 17/10/2022 | 16/11/2022 | TAPAS KUMAR GIRI | 40.13 | 34.72 | 86.52 | 100
4 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Champahati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000534/2022-2023 | 461/SMD | 17/02/2023 | 01/04/2026 | NUPUR CHANDRA HALDER | 19.65 | 8.84 | 45.01 | 70
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Construction of 500 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHAMPAHATI (Zone-II) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2991) | AE BSD | JE RWS | ORD/000570/2023-2024 | 2667/SWD-I | 31/10/2023 | 01/04/2025 | RKS ENGINEER & CONTRACTOR | 578.64 | 143.14 | 24.74 | 65
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of CHAMPAHATI (Zone-II) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/010745] | AE BSD | JE-2 | ORD/000455/2023-2024 | 2112/SWD-I | 30/08/2023 | 14/09/2023 | TAPAS KUMAR GIRI | 4.41 | 4.23 | 95.97 | 100
7 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 18.42 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Material Requisition To Resource Division |  |  | RTOR000302/2023-2024 | 2440/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 48.26 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01726/2023-2024 | BP-2023-24-198 | 09/08/2023 | 09/08/2023 | WBSEDCL | 7.37 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Champahati (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002470/2023-2024 | 289/SMSD | 07/03/2024 | 22/03/2024 | NUPUR CHANDRA HALDER | 0.8 | 0.79 | 99.12 | 100
11 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 (Zone-II) of Champahat W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12873) | Assistant Engineer | Junior Engineer | ORD/000219/2024-2025 | 926/SMSD | 28/06/2024 | 15/09/2025 | NUPUR CHANDRA HALDER | 0.58 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Additional quotation for power connection at Champahat Zone-II P-1 |  |  | BILL/00285/2024-2025 | BP-2024-25-76 | 22/05/2024 | 22/05/2024 | WBSEDCL | 1.04 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Augmentation of Champahati (Zone-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] (SM/12873) | Assistant Engineer | Junior Engineer | ORD/000050/2025-2026 | 1428/SMD | 21/05/2025 | 03/10/2025 | KARUNAMOY ENGINEERING | 10.97 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Champahati (Zone-II) W/S scheme under SMD, P.H.E. Dte.(SM/12873) | Assistant Engineer | Junior Engineer | ORD/001308/2025-2026 | 1032/SMSD | 22/07/2025 | 06/08/2025 | NUPUR CHANDRA HALDER | 0.63 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-2 of Champahati (Zone-II) W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/12873) | Assistant Engineer | Junior Engineer | ORD/001306/2025-2026 | 1030/SMSD | 22/07/2025 | 06/08/2025 | NUPUR CHANDRA HALDER | 0.83 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Supply & delivery of Actuator Valve at Pump House no-2 of Champahati (Zone-II) W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/12873) | Assistant Engineer | Junior Engineer | ORD/001307/2025-2026 | 1031/SMSD | 22/07/2025 | 06/08/2025 | NUPUR CHANDRA HALDER | 0.99 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | SM/12873 | New | Additional Charges for new connection at pump house no-II of Champahati (Zone-II) (Baruipur Block) |  |  | BILL/01705/2025-2026 |  | 08/08/2025 | 08/08/2025 | WBSEDCL | 10.03 | 0 | 0 | 0
Total | [13 empty] | 756.23 | 194.49 | 25.72