## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | SM/12883 | Augmentation | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Chak Jalsi PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE SWSD-II |  | ORD/000301/2022-2023 | 1879/SWD-I | 16/11/2022 | 16/12/2022 | TAPAS KUMAR GIRI | 30.07 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | SM/12883 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Chak jalsi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000393/2022-2023 | 3795/SMD | 29/12/2022 | 29/03/2023 | MASSK ENGINEERING WORKS | 22.36 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | SM/12883 | Augmentation | Preparation and submission of Detailed Project Report of "CHAK JALASI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000384/2022-2023 | 413/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.83 | 2.62 | 92.47 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | SM/12883 | Augmentation | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of CHAK JALSI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1611] | AE SWSD-II | JE3 | ORD/000598/2022-2023 | 3126/SWD-I | 24/02/2023 | 01/02/2025 | MD NURNABI CONSTRUCTION (NUMABISK1992@GMAIL.COM) | 435.58 | 24.47 | 5.62 | 25
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | SM/12883 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 629 | 19/05/2023 | 19/05/2023 | Resource Division | 22.37 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | SM/12883 | Augmentation | Construction of Boundary wall, FHTC Platform, approach road, land development, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based CHAK JALSI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. | AE S24D1,AE SWSD-II | JE3 | ORD/000281/2024-2025 | 3032/SWD-I | 02/07/2024 | 27/12/2025 | BASIR CONSTRUCTION | 195.85 | 0 | 0 | 25
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground Water Based Chak Jalsi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District | SM/12883 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell by Rotary method for Ground Water Based at head work site of CHAK JALSI Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/12883) | AE S24D1,AE SWSD-II | JE3 | ORD/000444/2024-2025 | 3894/SWD-I | 04/09/2024 | 01/06/2025 | PADMA ENGINEERING CO. | 19.14 | 0 | 0 | 100
Total | [13 empty] | 728.2 | 27.09 | 3.72