## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Repair / renovation / overhauling of Iron elimination Plant of 100 cum capacity (aprox) for Nischintapur Water Supply Scheme under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/013413] | AE SWSD-I |  | ORD/000327/2022-2023 | 2044/SWD-I | 30/11/2022 | 15/12/2022 | RAMASISH ENTERPRISE | 12.92 | 12.92 | 99.98 | 50
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Sinking of 02 (two) nos. Replacement Rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for water supply at Nandarampur W/S Scheme and Buita W/S Scheme of Budge Budge-I Block under South 24-Parganas W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000304/2022-2023 | 1884/SWD-I | 16/11/2022 | 16/12/2022 | SUBHRA ENTERPRISE | 30.03 | 26.46 | 88.12 | 50
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Nandarampur&Buita PWSS for repair and replacement of Tubewell zones of different W/S Scheme under Budge Budge-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/013413] | AE SWSD-I |  | ORD/000696/2022-2023 | 3499/SWD-I | 16/03/2023 | 31/03/2023 | SUBHRA ENTERPRISE | 3.14 | 3.14 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Repairing Rising Main from Existing Tubewell to existing OHR for BUITA Distribution Zone for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. South 24 Pgs. (TSM/013413) | AE SWSD-I |  | ORD/000746/2022-2023 | 3597/SWD-I | 23/03/2023 | 22/04/2023 | PEECON | 3.28 | 3.05 | 93.1 | 0
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories for replacement of Tube Well at different water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-I] | Assistant Engineer -II | Junior Engineer | ORD/000611/2022-2023 | 374/SMD | 13/02/2023 | 14/05/2023 | M/S. S.S. ENTERPRISE | 22.21 | 21.32 | 96 | 60
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Interconnection for Replacement Tubewell of Buita Water Supply Scheme under "Repair And Replacement of TubeWell Zones of Different Water Supply Scheme under Budge Budge-I Under South 24 Pgns. W/S Division-I, PHE Dte. (TSM/ 013413) | AE SWSD-I | JE-2 | ORD/000243/2023-2024 | 1440/SWD-I | 18/07/2023 | 17/08/2023 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 4.84 | 2.41 | 49.8 | 100
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Laying Rising Main from Existing Tubewell to existing OHR for JAMALPUR & MOUKHALI Distribution Zone with interconnection and bypass arrangement including interconnection of Distribution mains for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. South 24 Pgs. (TSM/013413) | AE SWSD-I |  | ORD/000780/2022-2023 | 3664/SWD-I | 29/03/2023 | 13/05/2023 | M/S. S.S. ENTERPRISE | 19.82 | 11.69 | 59 | 75
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Boundary Wall for proposed Pump House Site at Abhirampur for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. Sdouth 24 Pgs. (TSM/013413) | AE SWSD-I | JE-1 | ORD/000747/2022-2023 | 3598/SWD-I | 23/03/2023 | 22/05/2023 | SANJAY MIDDEY | 6.47 | 2.53 | 39.03 | 100
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Road restoration of Inter connection of DI pipeline with distribution in Uttar Roypur Water Supply Scheme Head Work Site for Repair And Replacement of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24-Partganas, W/S Division-I, PHE Dte. (TSM/013413) [2nd call] | AE SWSD-I | JE-1 | ORD/000717/2023-2024 | 360/SWD-I | 16/01/2024 | 15/02/2024 | SRIJON ENTERPRISE | 7.83 | 3.91 | 49.91 | 100
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Inter connection of DI pipeline with distribution in Uttar Roypur Water Supply Scheme Head Work Site for Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge -I Under South 24-Partganas, W/S Division-I, PHE Dte. (TSM/013413) | AE SWSD-I | JE-1 | ORD/000616/2023-2024 | 2800/SWD-I | 09/11/2023 | 24/12/2023 | SRIJON ENTERPRISE | 10.94 | 8.04 | 73.44 | 100
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Renovation of external illumination arrangement with other allied works at PH No-1 under Nandarampur Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-I) (SM/12884) | Assistant Engineer -II | Junior Engineer | ORD/002100/2023-2024 | 156-AE-II-SMD | 09/02/2024 | 24/02/2024 | MAA SUSOMA & COMPANY | 0.75 | 0.49 | 65.8 | 100
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24 Pgs W/S Division-I, PHE Dte, Dist. South 24 Pgs. | SM/12884 | Augmentation | Road restoration due to laying of pipeline at different nodes under repair and replacement of tubewell zones of different Water Supply Schemes under Budge Budge-I under South 24-Pgns. Water Supply Division-I, PHE Dte. District South 24-Parganas. (SM/12884) | AE SWSD-I | JE-1 | ORD/000781/2023-2024 | 809/SWD-I | 16/02/2024 | 01/04/2024 | PROJECT AND MAINTENANCE | 37.97 | 0 | 0 | 70
Total | [13 empty] | 160.19 | 95.96 | 59.9