## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site HAORI Village of Budge Budge-II under South 24-Pgns W/S Divn-I, PHE Dte. (TSM/015373) | AE SWSD-I |  | ORD/000340/2022-2023 | 2071/SWD-I | 01/12/2022 | 30/01/2023 | UNI DEVELOPERS AND CONTRACTORS | 6.2 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I |  | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 30/01/2023 | M/S. SREEJIT ENTERPRISE | 19 | 0.76 | 4 | 98
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Haori water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000297/2023-2024 | 1388/SMD | 25/05/2023 | 23/08/2023 | M/S. S.S. ENTERPRISE | 10.88 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for water supply at HAORI Piped Water Supply Scheme within Budge Budge-II Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000267/2022-2023 | 1778/SWD-I | 07/11/2022 | 07/12/2022 | MOMINUL BISWAS | 14.69 | 13.53 | 92.15 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method HAORI PWSS of Budge Budge-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district under South 24-Parganas W/S Divn- I, P.H.E. Dte. [SM/13297] [2nd Call] | AE SWSD-I |  | ORD/000680/2022-2023 | 3476/SWD-I | 15/03/2023 | 30/03/2023 | MOMINUL BISWAS | 2.17 | 2.17 | 100 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02498/2023-2024 | BP-2023-24-263 | 18/09/2023 | 18/09/2023 | WBSEDCL | 1.88 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01821/2022-2023 | BP-2022-23-464 | 23/03/2023 | 23/03/2023 | WBSEDCL | 1.04 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Interconnection from proposed Tubewell to existing Distribution Line with Laying of HDPE pipeline for distribution system & providing FHTC of HAORI piped water supply scheme for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. under South 24 Pgs W/S Division -I, P.H.E. Dte. | AE SWSD-I | JE-2 | ORD/000369/2022-2023 | 2313/SWD-I | 19/12/2022 | 19/03/2023 | SUKUMAR DEBNATH | 110.48 | 110.37 | 99.91 | 60
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Construction of Pump House (Size 4.80mX3.66m) at tubewell site HAORI Village of Budge Budge-II under South 24-Pgns W/S Divn-I, PHE Dte. (TSM/015373) | AE SWSD-I | JE-2 | ORD/000011/2023-2024 | 35/SWD-I | 05/04/2023 | 04/06/2023 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 6.79 | 6.2 | 91.3 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Haori water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000518/2022-2023 | 377/SMD | 15/02/2023 | 16/05/2023 | M/S. S.S. ENTERPRISE | 10.76 | 9.34 | 86.85 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Haori Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000993/2022-2023 | 1533/SWD-I | 29/09/2022 | 29/10/2022 | GEO SOLUTION | 2.45 | 2.44 | 99.48 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based HAORI piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas | SM/13297 | Augmentation | Supply & Delivery of additional materials for PH No.-1 of Haori Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Budge Budge - II) [SM/13297] | Assistant Engineer -II | Junior Engineer | ORD/002999/2023-2024 | 288/AE-II/SMD | 15/03/2024 | 30/03/2024 | M/S. S.S. ENTERPRISE | 0.26 | 0 | 0 | 100
Total | [13 empty] | 186.58 | 144.81 | 77.61