## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for USPARA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015202] | AE HQ-I |  | ORD/000606/2022-2023 | 3135/SWD-I | 27/02/2023 | 29/03/2023 | SABYASACHI CHAKI | 31.75 | 15.57 | 49.04 | 50
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 23.39 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 13.02 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02492/2023-2024 | BP-2023-24-262 | 18/09/2023 | 18/09/2023 | WBSEDCL | 5.63 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Uspara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000500/2022-2023 | 318/SMD | 06/02/2023 | 07/05/2023 | ORIENTAL ENGINEERING CO. | 23.51 | 10.85 | 46.15 | 45
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Additional Laying of distribution Network System for different dia HDPE pipe under Ushpara PWSS, Block-Bhangar-I, Dist-South 24 Parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2114]. [SM Code - SM/13307] [2nd Call] | AE HQ-I | JE-4 | ORD/000706/2023-2024 | 3403/SWD-I | 28/12/2023 | 26/02/2024 | I.S ENTERPRISE | 53.48 | 47.53 | 88.88 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Construction of Boundary Wall, Eucalyptus Bullah piling work with Drumsheet walling, Approach Road and Road Restoration of USHPARA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/13307) | AE HQ-I | JE-4 | ORD/000370/2024-2025 | 3529/SWD-I | 07/08/2024 | 05/11/2024 | I.S ENTERPRISE | 100.98 | 41.08 | 40.68 | 45
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for USHPARA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2114] | AE HQ-I | JE-4 | ORD/000713/2022-2023 | 3538/SWD-I | 20/03/2023 | 03/04/2025 | I.S ENTERPRISE | 429.22 | 287.48 | 66.98 | 30
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for USHPARA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13307] |  |  | ORD/001152/2024-2025 | 370/SWD-I | 04/02/2025 | 06/03/2025 | HI-LIGHT ELECTRONICS | 15.9 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Land development at HW & 2nd tube well site and restoration of road damaged due to laying of pipe line for USHPARA PWSS in Bhangar-I Block under South 24-Parganas, W/S Division-I, P.H.E. Dte. for Augmentation of Surface Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. District under Jal Jeevan Mission (SM/13307) | AE HQ-I | JE-4 | ORD/000871/2024-2025 | 4929/SWD-I | 03/12/2024 | 02/02/2025 | I.S ENTERPRISE | 60.86 | 0 | 0 | 50
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Ushapara PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/13307) | Assistant Engineer | Junior Engineer | ORD/003108/2023-2024 | 239/SMSD | 16/02/2024 | 02/03/2024 | ORIENTAL ENGINEERING CO. | 0.9 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | USPARA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13307 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Uspara W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/13307) | Assistant Engineer | Junior Engineer | ORD/003139/2023-2024 | 122/SMSD | 29/01/2024 | 13/02/2024 | ORIENTAL ENGINEERING CO. | 0.29 | 0 | 0 | 100
Total | [13 empty] | 758.94 | 402.52 | 53.04