## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Preparation and submission of Detailed Project Report of BRINDAKHALI(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000509/2021-2022 | 1942/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 2.76 | 2.64 | 95.84 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 3328/SWD-I | 09/03/2023 | 09/03/2023 | Resource Division | 10.92 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 28.44 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BRINDAKHALI-I PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13309] | AE BSD | JE RWS | ORD/000562/2022-2023 | 3059/SWD-I | 21/02/2023 | 23/03/2023 | ABDUL LOTIB MOLLA | 31.76 | 14.46 | 45.53 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.28] |  |  | BILL/00488/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 11.1 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04675/2023-2024 | BP-2023-24-511 | 12/02/2024 | 12/02/2024 | WBSEDCL | 11.18 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Brindakhali-I water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000477/2022-2023 | 3948/SMD | 30/12/2022 | 01/04/2025 | DEBJYOTI BASU | 22.21 | 0 | 0 | 40
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of BRINDAKHALI (Zone-I) Mouza of BARUIPUR Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 1773) [TSM/015376] | AE BSD | JE RWS | ORD/000062/2023-2024 | 366/SWD-I | 27/04/2023 | 28/12/2025 | M/S V.P. JAIN | 395.19 | 251.91 | 63.74 | 98
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Brindakhali (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13309) | Assistant Engineer | Junior Engineer | ORD/001392/2024-2025 | 1689/SMSD | 24/12/2024 | 08/01/2025 | DEBJYOTI BASU | 0.58 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Brindakhali (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13309) | Assistant Engineer | Junior Engineer | ORD/001391/2024-2025 | 1691/SMSD | 24/12/2024 | 08/01/2025 | DEBJYOTI BASU | 0.91 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Supply & installation of Vinyl printing ACP board at Head work site of Brindakhali (Zone-I) water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- SONARPUR ] | Assistant Engineer | Junior Engineer | ORD/001554/2024-2025 | 562/SMSD | 03/05/2024 | 18/05/2024 | S.S. SIGNS | 0.3 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Brindakhali (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13309) | Assistant Engineer | Junior Engineer | ORD/001390/2024-2025 | 1690/SMSD | 24/12/2024 | 08/01/2025 | DEBJYOTI BASU | 0.91 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District | SM/13309 | Augmentation | Construction of platform for FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based BRINDAKHALI ZONE-I Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/13309) | AE BSD | JE RWS | ORD/000338/2024-2025 | 3312/SWD-I | 23/07/2024 | 31/03/2026 | M/S V.P. JAIN | 91.18 | 0 | 0 | 60
Total | [13 empty] | 607.45 | 269.01 | 44.28