## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BRINDAKHALI-II PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. | AE BSD |  | ORD/000561/2022-2023 | 3057/SWD-I | 21/02/2023 | 23/03/2023 | M/S MONDAL ENTERPRISE | 15.88 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Preparation and submission of Detailed Project Report of BRINDAKHALI(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000510/2021-2022 | 1943/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 2.76 | 2.65 | 95.99 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 3387/SWD-I | 10/03/2023 | 10/03/2023 | Resource Division | 7.28 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 1.46 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BRINDAKHALI-II PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13310] | AE BSD | JE RWS | ORD/000389/2024-2025 | 3607/SWD-I | 14/08/2024 | 29/08/2024 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 14.2 | 89.4 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Road restoration for Ramnagar Bazar to Matiar Dhali House. |  |  | BILL/01694/2024-2025 | BP-2024-25-783 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.08 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04625/2023-2024 | BP-2023-24-484 | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Brindakhali-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000478/2022-2023 | 3949/SMD | 30/12/2022 | 01/04/2025 | DEBJYOTI BASU | 11.19 | 0 | 0 | 80
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Construction of 200 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (1 No.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of BRINDAKHALI (Zone-II) Mouza of BARUIPUR Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 1182) [TSM/015225] | AE BSD | JE RWS | ORD/000061/2023-2024 | 365/SWD-I | 27/04/2023 | 01/10/2025 | M/S V.P. JAIN | 335.23 | 248.87 | 74.24 | 94
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Brindakhali (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13310) | Assistant Engineer | Junior Engineer | ORD/001389/2024-2025 | 1685/SMSD | 24/12/2024 | 08/01/2025 | DEBJYOTI BASU | 0.29 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based BRINDAKHALI-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Distric | SM/13310 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Brindakhali (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13310) | Assistant Engineer | Junior Engineer | ORD/001393/2024-2025 | 1686/SMSD | 24/12/2024 | 08/01/2025 | DEBJYOTI BASU | 0.91 | 0 | 0 | 100
Total | [13 empty] | 396.49 | 265.72 | 67.02