## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Preparation and submission of Detailed Project Report of NABAGRAM Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000367/2021-2022 | 1944/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 2.76 | 2.76 | 100 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 45.61 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03275/2023-2024 | BP-2023-24-365 | 04/11/2023 | 04/11/2023 | WBSEDCL | 3.49 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at NABAGRAM of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 2040] | AE BSD | JE-1 | ORD/000024/2023-2024 | 96/SWD-I | 10/04/2023 | 09/07/2023 | TANMOY ROY CHOWDHURY | 459.09 | 276.84 | 60.3 | 80
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Balance miscellaneous work for Ground water based NABAGRAM Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/13311) |  |  | ORD/000905/2023-2024 | 1204/SWD-I | 11/03/2024 | 25/04/2024 | R. UNIQUE CONSTRUCTION | 40.41 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 ,2 & 3 of NABAGRAM W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13311) | Assistant Engineer | Junior Engineer | ORD/000344/2024-2025 | 890/SMSD | 19/06/2024 | 04/07/2024 | SWAPAN ENTERPRISE | 0.87 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Nabagram W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002473/2023-2024 | 276/SMSD | 29/02/2024 | 15/03/2024 | SWAPAN ENTERPRISE | 0.92 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for NABAGRAM PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. | AE BSD | JE-1,JE-2 | ORD/000564/2022-2023 | 3058/SWD-I | 21/02/2023 | 23/03/2023 | MD NOOR ALAM | 47.63 | 32.68 | 68.61 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Charges for new service connection at pump house no -2 of Nabagram (Baruipur Block) |  |  | BILL/01981/2024-2025 | BP-2024-25-482 | 03/12/2024 | 03/12/2024 | WBSEDCL | 15.91 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Charges for new service connection at pump house no-3 of Nabagram-3 |  |  | BILL/01723/2024-2025 | BP-2024-25-412 | 30/09/2024 | 30/09/2024 | WBSEDCL | 3.81 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Nabagram water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000481/2022-2023 | 234/SMD | 24/01/2023 | 01/04/2026 | SWAPAN ENTERPRISE | 39.02 | 0 | 0 | 73
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Nabagram scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13311) | Assistant Engineer | Junior Engineer | ORD/000353/2024-2025 | 1003/SMSD | 11/07/2024 | 01/08/2025 | SWAPAN ENTERPRISE | 0.92 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13311 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Nabagram scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13311) | Assistant Engineer | Junior Engineer | ORD/000354/2024-2025 | 1004/SMSD | 11/07/2024 | 01/08/2025 | SWAPAN ENTERPRISE | 0.92 | 0 | 0 | 100
Total | [13 empty] | 661.35 | 312.28 | 47.22