## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 21.02 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 11.96 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for BHATIPOTA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015204] | AE HQ-I | JE-4 | ORD/000621/2022-2023 | 3235/SWD-I | 01/03/2023 | 31/03/2023 | SETABUR RAHAMAN | 31.67 | 15.18 | 47.93 | 50
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bhatipota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000501/2022-2023 | 319/SMD | 06/02/2023 | 07/05/2023 | ORIENTAL ENGINEERING CO. | 23.51 | 10.8 | 45.92 | 45
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Additional Laying of distribution Network System for different dia HDPE pipe under Bhatipota PWSS, Block-Bhangar-I, Dist-South 24 Parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1942] (SM/13341) | AE HQ-I | JE-4 | ORD/000617/2023-2024 | 2801/SWD-I | 09/11/2023 | 08/01/2024 | K.K. BUILDER. | 34.34 | 34.28 | 99.81 | 55
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Construction of 02 (Two) nos. Pipe Carrying Structure- Near Bhatipota OHR Site over 56.0 mtr. width canal and Near Kolkata-Basanti Highway,opp. Kolkata Leather Complex Police Station over 66.0 mtr. width canal within Bhatipota Mouza of Tardaha GP under Bhangar-I Block, BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I | JE-4 | ORD/000738/2023-2024 | 523/SWD-I | 29/01/2024 | 14/03/2024 | GANAPATI ENTERPRISE | 31.83 | 31.74 | 99.72 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Bhatipota PH-1 under Bhangar-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2024-2025 | 458/SMSD | 16/04/2024 | 01/05/2024 | ORIENTAL ENGINEERING CO. | 0.89 | 0.89 | 100 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Restoration of Road Side Flank damaged by PHE Department under Bhojerhat Pipe Line Project from 3,872 km to 4.195 km (Left Side) 3.475 km to 4.095km (RS) [Total Length - 943.00m] under South 24 Parganas Highway Division" |  |  | BILL/00546/2024-2025 | BP-2024-25-338 | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.23 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | "ANANDAPUR-KHARKI-BOYNALA-TARDAH ROAD-Restoration of road side flank damaged by PHE Department under bhojerhat pipeline project from 3.872 km to 4.195 km (left side),3.475 km to 4.095 km (R/S),[Total length=943.00m] under South 24-Parganas Highway Division." |  |  | BILL/00497/2024-2025 |  | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 12.1 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04622/2023-2024 | BP-2023-24-481 | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Kolkata Basanti Road from 12.427 km to 15.581 km, Permanent restoration work , damaged due to " Pipeline Laying of 90mm,140mm, & 225mm dia HDPE Pipoe Line along road flank by PHE Department " within Alipore Highway Sub-Division under South 24 Parganas Highway Division in the District of South 24 Parganas. (SM/13341) |  |  | BILL/00850/2024-2025 | BP-2024-25-504 | 11/12/2024 | 11/12/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.92 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | 50% Payment for ANANDAPUR-KHARKI-BOYNALA-TARDAH ROAD-Restoration of road side flank damaged by PHE Department under bhojerhat pipeline project from 3.872 km to 4.195 km (left side),3.475 km to 4.095 km (R/S),[Total length=943.00m] under South 24-Parganas Highway Division |  |  | BILL/00534/2024-2025 | BP-2024-25-308 | 18/09/2024 | 18/09/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.05 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1942] | AE HQ-I | JE-4 | ORD/000710/2022-2023 | 3527/SWD-I | 17/03/2023 | 12/05/2025 | K.K. BUILDER. | 465.21 | 386.71 | 83.12 | 70
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I | JE-4 | ORD/000765/2024-2025 | 4686/SWD-I | 18/11/2024 | 17/01/2025 | K.K. BUILDER | 23.12 | 0 | 0 | 52
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Construction of Boundary Wall, Eucalyptus Bullah piling work with Drumsheet walling, Approach Road and Road Restoration of BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I,AE HQ-II | JE-4 | ORD/000260/2024-2025 | 2857/SWD-I | 20/06/2024 | 22/03/2025 | BOSE ENTERPRISES | 164.67 | 101.27 | 61.5 | 45
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under TARDAH KAPASATI, BHATIPOTA, KHARAMBA & SHERPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18501, SM/13341, SM/18545 & SM/18500) | AE HQ-I | JE-4 | ORD/000508/2024-2025 | 3977/SWD-I | 11/09/2024 | 26/10/2024 | TELETONE INDIA PRIVATE LIMITED | 107.09 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM | SM/13341 | Augmentation | Additional Laying of distribution Network System for different dia HDPE pipe & providing FHTC under "BHATIPOTA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district Under JJM" [No. of FHTC = 450]. [SM Code - SM/13341] | AE HQ-I,AE HQ-II | JE-4 | ORD/000832/2023-2024 | 1281/SWD-I | 14/03/2024 | 13/05/2025 | K.K. BUILDER | 30.1 | 21.79 | 72.38 | 80
Total | [13 empty] | 980.47 | 602.64 | 61.46