## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Preparation and submission of Detailed Project Report of CHADOKHALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000347/2021-2022 | 1907/SWD-I | 27/01/2022 | 26/02/2022 | TECH VISION | 3.03 | 2.75 | 90.7 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 294/SWD-I | 25/04/2023 |  | Resource Division | 23.82 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01506/2023-2024 | BP-2023-24-242 | 11/09/2023 |  | WBSEDCL | 2.45 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Construction of Pump house / chlorination room at 3rd Tubewell site for Augmentation of ground water based CHADOKHALI PWSS to accomodatte FHTC in Baruipur Block under South 24-Pgns, W/S Divn-I, PHE Dte. within South 24-Pgns district. [TSM/014213] [2nd call] | AE BSD |  | ORD/000521/2023-2024 | 2268/SWD-I | 14/09/2023 | 13/11/2023 | MOLLICK ENTERPRISE | 5.68 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02287/2023-2024 | BP-2023-24-261 | 18/09/2023 |  | WBSEDCL | 3.49 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHADOKHALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000277/2022-2023 | 1839/SWD-I | 11/11/2022 | 11/12/2022 | G D S ENTERPRISE | 39.87 | 35.69 | 89.5 | 100
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chadokhali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014213] | AE BSD |  | ORD/000786/2022-2023 | 3668/SWD-I | 29/03/2023 | 13/04/2023 | G.D.S ENTERPRISE | 4.39 | 4.21 | 95.97 | 100
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Construction of 02 (Two) nos. chlorination room at CHADOKHALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014213] | AE BSD | JE-2 | ORD/000252/2022-2023 | 1753/SWD-I | 04/11/2022 | 03/01/2023 | MA TARA CONSTRUCTION | 10.93 | 4.3 | 39.3 | 50
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03348/2023-2024 | BP-2023-24-368 | 08/11/2023 |  | WBSEDCL | 8.76 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by having 66 mtr. Housing by Rotary method for 3rd tubewell site for Augmentation of ground water based CHADOKHALI PWSS to accomodate FHTC in Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/014213] | AE BSD |  | ORD/000229/2023-2024 | 1405/SWD-I | 14/07/2023 | 13/08/2023 | M/S. S M ENTERPRISE | 21.54 | 10.03 | 46.55 | 100
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Chadokhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000475/2022-2023 | 3946/SMD | 30/12/2022 | 30/03/2023 | WEST BENGAL ENGINEERING CO. | 32.24 | 9.67 | 30 | 60
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Construction of Boundary walls, platform for providing FHTC, Approach road and other allied works for Augmentation of Ground water based Chadokhali piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte.(SM/13441) |  |  | ORD/000352/2024-2025 | 3452/SWD-I | 02/08/2024 | 16/09/2024 | M/S. JAYDEEP DASGUPTA | 93.01 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Chadokhali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002708/2023-2024 | 1401/SMSD | 17/11/2023 | 02/12/2023 | WEST BENGAL ENGINEERING CO. | 0.58 | 0.58 | 100 | 100
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Chadokhali W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002710/2023-2024 | 1403/SMSD | 17/11/2023 | 02/12/2023 | WEST BENGAL ENGINEERING CO. | 0.9 | 0.9 | 99.81 | 100
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Chadokhali W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002709/2023-2024 | 1402/SMSD | 17/11/2023 | 02/12/2023 | WEST BENGAL ENGINEERING CO. | 0.9 | 0.37 | 41.07 | 100
16 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-3 of of Chadokhali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13441) | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 675/SMSD | 04/06/2024 | 19/06/2024 | WEST BENGAL ENGINEERING CO. | 0.55 | 0 | 0 | 0
17 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Chadokhali W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/13441) | Assistant Engineer | Junior Engineer | ORD/000278/2024-2025 | 643/SMSD | 29/05/2024 | 13/06/2024 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 0 | 0
18 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at CHADOKHALI of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 988) | AE BSD | JE RWS,JE-2 | ORD/000282/2022-2023 | 1843/SWD-I | 11/11/2022 | 09/02/2023 | J.D. CONSTRUCTION | 153.54 | 129.46 | 84.31 | 100
19 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Balance work for Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at CHADOKHALI for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [No. of FHTC =1517] [TSM/014213] | AE BSD | JE RWS,JE-2 | ORD/000052/2023-2024 | 271/SWD-I | 24/04/2023 | 23/07/2023 | J.D. CONSTRUCTION | 221.14 | 106.75 | 48.27 | 45
20 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based CHADOKHALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13441 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.29] |  |  | BILL/00489/2024-2025 | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 4.06 | 0 | 0 | 0
Total | [13 empty] | 631.82 | 304.7 | 48.23