## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Preparation and submission of Detailed Project Report of ALIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000346/2021-2022 | 1908/SWD-I | 27/01/2022 | 26/02/2022 | TECH VISION | 2.76 | 2.74 | 99.37 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 294/SWD-I | 25/04/2023 |  | Resource Division | 14.32 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Alipur PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014211] | AE BSD |  | ORD/000781/2022-2023 | 3665/SWD-I | 29/03/2023 | 13/04/2023 | UMAR ALI KHAN | 4.4 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Alipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000476/2022-2023 | 3947/SMD | 30/12/2022 | 30/03/2023 | BARISAL TRADING CO. | 21.5 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/00287/2023-2024 | BP-2023-24-17 | 15/05/2023 |  | WBSEDCL | 5.87 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Construction of 02 (Two) nos. chlorination room at ALIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014211] | AE BSD |  | ORD/000251/2022-2023 | 1752/SWD-I | 04/11/2022 | 03/01/2023 | B.M. TRADERS | 10.93 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for ALIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000275/2022-2023 | 1838/SWD-I | 11/11/2022 | 11/12/2022 | UMAR ALI KHAN | 40.12 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04653/2023-2024 | BP-2023-24-492 | 12/02/2024 |  | WBSEDCL | 3.42 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04653/2023-2024 | BP-2023-24-492 | 12/02/2024 |  | WBSEDCL | 3.42 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Balance work for Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at ALIPUR for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [No. of FHTC =244] [TSM/014211] | AE BSD | JE-2 | ORD/000167/2023-2024 | 964/SWD-I | 08/06/2023 | 06/09/2023 | RAJ KUMAR MONDAL | 122.78 | 36.26 | 29.53 | 40
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at ALIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1186) | AE BSD | JE-2 | ORD/000323/2022-2023 | 2020/SWD-I | 29/11/2022 | 27/02/2023 | RAJ KUMAR MONDAL | 190.68 | 52.95 | 27.77 | 65
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Alipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13442) | Assistant Engineer | Junior Engineer | ORD/000316/2024-2025 | 939/SMSD | 28/06/2024 | 13/07/2024 | BARISAL TRADING CO. | 0.58 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Alipur scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13442) | Assistant Engineer | Junior Engineer | ORD/000314/2024-2025 | 1010/SMSD | 11/07/2024 | 26/07/2024 | BARISAL TRADING CO. | 0.89 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Alipur scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13442) | Assistant Engineer | Junior Engineer | ORD/000315/2024-2025 | 1011/SMSM | 11/07/2024 | 26/07/2024 | BARISAL TRADING CO. | 0.89 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24- pgns W/S Division-I, South 24 Parganas District. | SM/13442 | Augmentation | Construction of boundary wall, platform for FHTC, road restoration, protection work for pipeline and other allied works for Ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte, South 24 Parganas district. (SM/13442) |  |  | ORD/000509/2024-2025 | 3964/SWD-I | 10/09/2024 | 09/11/2024 | SANDHYA ENTERPRISE | 58.48 | 0 | 0 | 0
Total | [13 empty] | 481.03 | 91.95 | 19.12