## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Preparation and submission of Detailed Project Report of GARIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000311/2021-2022 | 1955/SWD-I | 27/01/2022 | 26/02/2022 | ENVIROTECH SOLUTIONS | 2.76 | 2.76 | 100 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 22.21 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 3423/SWD-I | 13/03/2023 | 13/03/2023 | Resource Division | 12.14 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Construction of Platform for providing FHTC for Ground Water Based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/13443) |  |  | ORD/000303/2024-2025 | 3216/SWD-I | 18/07/2024 | 16/09/2024 | TIRUPATI ENTERPRISES | 36.67 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for GARIA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13443] | AE BSD | JE-1 | ORD/000567/2022-2023 | 3063/SWD-I | 21/02/2023 | 23/03/2023 | M/S MONDAL ENTERPRISE | 31.75 | 18.76 | 59.09 | 50
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Charges for new connection at pump house no-1 of Garia water supply scheme (Baruipur Block) |  |  | BILL/01898/2024-2025 | BP-2024-25-481 | 28/11/2024 | 28/11/2024 | WBSEDCL | 4.03 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Garia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000479/2022-2023 | 232/SMD | 24/01/2023 | 02/06/2025 | DEBJYOTI BASU | 26.02 | 0 | 0 | 40
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Laying distribution system, Rising Main, Functional House Hold Tap Connection (FHTC) alongwith construction of Chlorine Room (two nos.) for Augmentation of GARIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [No. of FHTC = 1970] [TSM/015205] | AE BSD | JE-1 | ORD/000626/2023-2024 | 20/SWD-I | 05/04/2023 | 20/03/2026 | TIRUPATI ENTERPRISES | 360.05 | 229.88 | 63.85 | 85
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Garia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13443) | Assistant Engineer | Junior Engineer | ORD/000263/2025-2026 | 705/SMSD | 08/05/2025 | 23/05/2025 | DEBJYOTI BASU | 0.93 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/13443 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Garia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13443) | Assistant Engineer | Junior Engineer | ORD/000261/2025-2026 | 505/SMSD | 04/04/2025 | 19/04/2025 | DEBJYOTI BASU | 0.58 | 0 | 0 | 0
Total | [13 empty] | 497.14 | 251.4 | 50.57