## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Preparation and submission of Detailed Project Report of MALLIKPUR , PART-III Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000204/2021-2022 | 1920/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.76 | 2.72 | 98.67 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 295/SWD-I | 25/04/2023 |  | Resource Division | 42.16 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Mallickpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000480/2022-2023 | 233/SMD | 24/01/2023 | 24/04/2023 | DEBJYOTI BASU | 33.34 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALLIKPUR (PART-III) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1718] [TSM/012612] | AE BSD |  | ORD/000105/2023-2024 | 482/SWD-I | 08/05/2023 | 06/08/2023 | RANJIT KAR | 161.99 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/00620/2023-2024 | BP-2023-24-90 | 14/06/2023 |  | WBSEDCL | 0.08 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3, & 4 for Augmentation of Mallikpur Part-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000060/2023-2024 | 1054/SMD | 18/04/2023 | 17/07/2023 | M/S. S.S. ENTERPRISE | 50.65 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Construction of chlorination room at MALLICKPUR (Part-I) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district South 24-Pgns W/S Divn.-I, PHE Dte. | AE BSD |  | ORD/000287/2022-2023 | 1781/SWD-I | 07/11/2022 | 06/01/2023 | M/S. FAIZUL HAQUE BISWAS | 5.75 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based MALLICKPUR piped water supply scheme (PART-III) to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas | SM/13444 | Augmentation | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MALLICKPUR (PART-III) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13444] | AE BSD | JE-1 | ORD/000569/2022-2023 | 3065/SWD-I | 21/02/2023 | 23/03/2023 | MD NURUZZUMAN (EMAIL ID- MDNGRPKR@GMAIL.COM) | 47.64 | 7.54 | 15.82 | 34
Total | [13 empty] | 344.36 | 10.26 | 2.98