## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kashidanga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000499/2022-2023 | 317/SMD | 06/02/2023 | 06/07/2025 | B.T.PROJECTS PVT.LTD. | 26.78 | 24.89 | 92.92 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KASHIA DANGA PWSS of BHANGAR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014455] | AE HQ-I | JE-4 | ORD/000604/2022-2023 | 3134/SWD-I | 27/02/2023 | 29/03/2023 | KUNTAL CHOWDHURY | 31.76 | 31.55 | 99.33 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for KASHIADANGA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1406] | AE HQ-I | JE-4 | ORD/000752/2022-2023 | 3619/SWD-I | 24/03/2023 | 22/05/2025 | BABLU KUMAR MONDAL | 496.35 | 424.51 | 85.53 | 55
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 11 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000222/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 8.66 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of KASHIADANGA PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13512) | AE HQ-I | JE-4 | ORD/000668/2024-2025 | 4415/SWD-I | 24/10/2024 | 22/04/2026 | BABLU KUMAR MONDAL (Partnership Firm) | 121.32 | 0 | 0 | 50
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Kashiadanga PH-2 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2024-2025 | 576/SMSD | 10/05/2024 | 25/05/2024 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kashiadanga, PH-1 under Bhangar-I Block water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000543/2024-2025 | 818/SMSD | 11/06/2024 | 26/06/2024 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Kashiadanga water supply scheme under South 24-Pgs Mechanical Division PHE Dte.[Bhangar-I] [SM/13512] | Assistant Engineer | Junior Engineer | ORD/000868/2024-2025 | 624/SMSD | 21/05/2024 | 05/06/2024 | SHRI KRISHNA ENTERPRISE | 0.78 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Kashiadanga W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/13512) | Assistant Engineer | Junior Engineer | ORD/002405/2024-2025 | 921-SMSD | 26/06/2024 | 11/07/2024 | B.T.PROJECTS PVT.LTD. | 0.58 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KASHIADANGA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13512 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04623/2023-2024 | BP-2023-24-480 | 07/02/2024 | 07/02/2024 | WBSEDCL | 14.26 | 0 | 0 | 0
Total | [13 empty] | 713.27 | 480.95 | 67.43