## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s | SM/13513 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for zone-VII, Ajodhyanagar (OHR Cap-450 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II |  | ORD/000308/2021-2022 | 2606/SWD-I | 15/03/2022 | 14/04/2022 | MS R. DUTTA AND CO | 1.98 | 1.92 | 96.79 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s | SM/13513 | Augmentation | Laying distribution system of pipe water supply scheme in ZONE-VII AT AJODHYANAGAR of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 3427 Nos.) | AE SWSD-II | JE1 | ORD/000515/2022-2023 | 2881/SWD-I | 13/02/2023 | 07/11/2025 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 379.95 | 88.57 | 23.31 | 79
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s | SM/13513 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 284/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 20.45 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s | SM/13513 | Augmentation | Construction of chlorination room, land development, repairing and renovation boundary wall and other allied works for Zone-VII (Ajodhyanagar) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. | AE SWSD-II | JE1 | ORD/000742/2024-2025 | 4640/SWD-I | 14/11/2024 | 28/01/2025 | M/S SHIBAM ENTERPRISE | 130.62 | 0 | 0 | 2
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s | SM/13513 | Augmentation | Interconnection between the new distribution pipeline and the outlet of the existing OHR as well as making a by-pass arrangement in the premises of Head Work site for Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I Block within ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District-South 24 Parganas¿ under South 24 Pgs W/S Division-I, P.H.E. Dte. (SM/13513) | AE SWSD-II | JE1 | ORD/000024/2025-2026 | 976/SWD-I | 09/04/2025 | 24/05/2025 | SRIJON ENTERPRISE | 18.08 | 0 | 0 | 94
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water s | SM/13513 | Augmentation | Laying of leftout distribution pipeline to interconnect the branch line with the main distribution line along and across the NH-117 for Augmentation of Laying Distribution System to extend the benefit of 100% house hold in Zone-VII (Ajodhyanagar) under Magrahat-I Block within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas¿ under South 24 Pgs W/S Division -I, P.H.E. Dte. (SM/13513) | AE S24D1 | JE1 | ORD/000007/2025-2026 | 910/SWD-I | 02/04/2025 | 01/07/2025 | P ENTERPRISE | 25.49 | 0 | 0 | 98
Total | [13 empty] | 576.58 | 90.49 | 15.69