## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DARI MADHABPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014441] | AE HQ-I |  | ORD/000605/2022-2023 | 3136/SWD-I | 27/02/2023 | 29/03/2023 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 31.78 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 13.13 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000220/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 13.15 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01497/2023-2024 | BP-2023-24-178 | 02/08/2023 | 02/08/2023 | WBSEDCL | 7.5 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for DARI MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2135] (TSM/014441) | AE HQ-I | JE-4 | ORD/000097/2023-2024 | 466/SWD-I | 04/05/2023 | 02/08/2023 | PROJECT INDIA | 412.54 | 0 | 0 | 85
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dari Madhabpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000502/2022-2023 | 320/SMD | 06/02/2023 | 07/05/2023 | ORIENTAL ENGINEERING CO. | 26.02 | 0 | 0 | 90
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of "DARI MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13674) |  |  | ORD/000677/2024-2025 | 4466/SWD-I | 29/10/2024 | 28/12/2024 | PROJECT INDIA | 79.05 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Supply & installation of LED board at PH-I & 2 of Dari Madhabpur water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Bhangar-I ] | Assistant Engineer | Junior Engineer | ORD/000003/2024-2025 | 1647/SMSD | 05/04/2024 | 20/04/2024 | KARTICK BAL | 0.78 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Dari Madhabpur PH-1 , under Bhangar-I block water supply scheme under SMD, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002283/2023-2024 | 1633/SMSD | 02/01/2024 | 17/01/2024 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Dari Madhabpur PH-2 , under Bhangar-I block water supply scheme under SMD, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002284/2023-2024 | 1634/SMSD | 02/01/2024 | 17/01/2024 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Continuation for the work of Engagement of 01 no. Computer Operator / Data Entry Operator [Category - A] for the office works of Executive Engineer (Deputed from PWD) under Superintending Engineer, South 24-Parganas W/S Circle, PHE Dte. [w.e.f. 01.04.2024 to 31.06.2024] | AE HQ-II | JE-2 | ORD/000902/2023-2024 | 1467/SWD-I | 27/03/2024 | 27/06/2024 | M/S. SYSCON | 0.51 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Continuation order for the work of Engagement of 01 no. Computer Operator / Data Entry Operator [Category - C] for the office works of Superintending Engineer, PMU, WBDWSIP (ADB), PHE Dte. under Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01.04.2024 to 31.06.2024] | AE HQ-II | JE-2 | ORD/000903/2023-2024 | 1468/SWD-I | 27/03/2024 | 27/06/2024 | M/S. SYSCON | 0.41 | 0 | 0 | 99
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | DARI MADHABPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/13674 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no- 1 & 2 of Dari Madhabpur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/13674) | Assistant Engineer | Junior Engineer | ORD/003140/2023-2024 | 51/SMSD | 11/01/2024 | 26/01/2024 | ORIENTAL ENGINEERING CO. | 0.58 | 0 | 0 | 0
Total | [13 empty] | 587.22 | 0 | 0