## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 286/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 23.87 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000230/2023-2024 | 1006/SWD-I | 09/06/2023 | 09/06/2023 | Resource Division | 10.62 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01986/2023-2024 | BP-2023-24-241 | 11/09/2023 | 11/09/2023 | WBSEDCL | 4.52 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1724] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000495/2022-2023 | 2863/SWD-I | 09/02/2023 | 28/07/2025 | MAHI ENTERPRISE | 372.71 | 103.04 | 27.65 | 25
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | Assistant engineer (contractual) | JE-3 | ORD/000822/2023-2024 | 1296/SWD-I | 15/03/2024 | 29/04/2024 | MAHI ENTERPRISE | 44.33 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Construction of Boundary Wall, Pathway, Drain, Development of land at proposed Headwork site of CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) |  |  | ORD/000726/2024-2025 | 4603/SWD-I | 12/11/2024 | 11/01/2025 | MAHI ENTERPRISE | 37.97 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Chakberia W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002380/2023-2024 | 279/SMSD | 29/02/2024 | 02/04/2025 | GHOSE ENGINEERING SYNDICATE | 0.9 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Additional laying of pipeline and restoration of road near PROPOSED OHR site of "CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13771) |  |  | ORD/000748/2024-2025 | 4670/SWD-I | 18/11/2024 | 02/01/2025 | MAHI ENTERPRISE | 21.74 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Construction of Hume Pipe Culvert 4.80 Mtr.span with 32 Mtr. Long temporary approach road (Plot No-35) for proposed Chakberia OHR Site at Navasan Mouza (JL No-109, Dag No-35, Khatian No-01) at CHAKBERIA PWSS within Sonarpur Block " CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | Assistant engineer (contractual) | JE-3 | ORD/000568/2024-2025 | 4241/SWD-I | 30/09/2024 | 01/02/2025 | MAHI ENTERPRISE | 13.38 | 1.94 | 14.49 | 60
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE CHAKBERIA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016026) | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000346/2022-2023 | 2164/SWD-I | 09/12/2022 | 01/01/2025 | ARASTA ENGINEERING & CO | 29.84 | 18 | 60.32 | 100
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHAKBERIA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13771] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000726/2022-2023 | 3575/SWD-I | 22/03/2023 | 11/01/2025 | ARASTA ENGINEERING & CO | 3.13 | 1.57 | 50 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Chakberia W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/13771) | Assistant Engineer | Junior Engineer | ORD/002254/2024-2025 | 444/SMSD | 21/03/2025 | 05/04/2025 | GHOSE ENGINEERING SYNDICATE | 0.85 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | CHAKBERIA piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/13771 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Chakberia W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/13771) | Assistant Engineer | Junior Engineer | ORD/002255/2024-2025 | 53/SMSD | 09/01/2025 | 24/01/2025 | GHOSE ENGINEERING SYNDICATE | 0.59 | 0 | 0 | 100
Total | [13 empty] | 564.46 | 124.55 | 22.06