## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/13776 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for KAMARIA (Zone-II) PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016159] | AE BSD |  | ORD/000503/2022-2023 | 2894/SWD-I | 13/02/2023 | 15/03/2023 | PURE RENOVATION GROUP | 31.78 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/13776 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 65.22 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/13776 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01750/2023-2024 | BP-2023-24-209 | 11/08/2023 | 11/08/2023 | WBSEDCL | 20.67 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/13776 | Augmentation | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of KAMARIA (ZONE-II) MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2051] [TSM/016159] | AE BSD | JE-1 | ORD/000170/2023-2024 | 967/SWD-I | 08/06/2023 | 03/04/2024 | MANASH GHOSH | 359.97 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/13776 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00002/2024-2025 | BP-2024-25-01 | 05/04/2024 | 05/04/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/13776 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamaria Zone-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000579/2022-2023 | 608/SMD | 28/02/2023 | 01/04/2025 | CONCORD ENGINEERING | 19.48 | 0 | 0 | 45
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KAMARIA ZONE - II piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/13776 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Kamaria Zone-II W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/13776) | Assistant Engineer | Junior Engineer | ORD/002357/2024-2025 | 1534/SMSD | 19/11/2024 | 04/12/2024 | CONCORD ENGINEERING | 0.88 | 0 | 0 | 0
Total | [13 empty] | 501.78 | 0 | 0