## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Preparation and submission of Detailed Project Report of BEGAMPUR(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000447/2021-2022 | 1952/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100 | 100
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Purba Begampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000482/2022-2023 | 235/SMD | 24/01/2023 | 01/10/2025 | S. DUTTA | 23.29 | 10.56 | 45.34 | 40
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of PURBO BEGAMPUR (ZONE-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1967] [TSM/011437] | AE BSD | JE RWS | ORD/000360/2023-2024 | 1763/SWD-I | 10/08/2023 | 27/05/2026 | ROSENBLUTH CONSTRUCTION PRIVATE LIMITED | 670.09 | 150.8 | 22.5 | 55
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PURBA BEGAMPUR (Zone-II) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13779] | AE BSD | JE RWS,JE-1 | ORD/000565/2022-2023 | 3061/SWD-I | 21/02/2023 | 23/03/2023 | M/S B.M. INDUSTRIES (BM.INDUSTRY@GMAIL.COM) | 31.76 | 30.88 | 97.23 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 27.14 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Purba Begampur (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13779) | Assistant Engineer | Junior Engineer | ORD/000352/2024-2025 | 924/SMSD | 28/06/2024 | 13/07/2024 | S. DUTTA | 0.58 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Purba Begampur (Zone-II) W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13779) | Assistant Engineer | Junior Engineer | ORD/000350/2024-2025 | 965/SMSD | 09/07/2024 | 24/07/2024 | S. DUTTA | 0.89 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Construction of Boundary walls, Pipeline protection, Platform for FHTC, Land development and other allied works for Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns District.(SM/13779) |  |  | ORD/000353/2024-2025 | 3453/SWD-I | 02/08/2024 | 16/09/2024 | SRIJON ENTERPRISE | 80.58 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Purba Begampur (Zone-II) W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13779) | Assistant Engineer | Junior Engineer | ORD/000351/2024-2025 | 964/SMSD | 09/07/2024 | 24/07/2024 | S. DUTTA | 0.89 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Road restoration for Chiner More to Haral Bani Scociation Bituminaous Via Punri Katpole to Bonabibi Tala |  |  | BILL/01696/2024-2025 | BP-2024-25-785 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.12 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distr | SM/13779 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Purba Begampur (Zone-II) water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | Assistant Engineer | Junior Engineer | ORD/000022/2025-2026 | 537/SMSD | 09/04/2025 | 30/04/2025 | FORTUNE ENGINEERING | 0.79 | 0 | 0 | 100
Total | [13 empty] | 839.88 | 194.99 | 23.22