## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Preparation and submission of Detailed Project Report of DAULATOUR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000420/2021-2022 | 1968/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.75 | 99.66 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for DAULATPUR PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016355] | AE SWSD-II | JE3 | ORD/000578/2022-2023 | 3093/SWD-I | 23/02/2023 | 25/03/2023 | MD RUHUL AMIN GOLDER | 15.89 | 13.83 | 87.07 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 39.25 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Daulatpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000510/2022-2023 | 349/SMD | 09/02/2023 | 10/05/2023 | AHALYA ENGINEERING WORKS | 22.87 | 10.38 | 45.38 | 40
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DAULATPUR Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13780] | AE SWSD-II | JE3 | ORD/000689/2024-2025 | 4484/SWD-I | 30/10/2024 | 29/11/2024 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of DAULATPUR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/016355] | AE SWSD-II | JE3 | ORD/000042/2023-2024 | 183/SWD-I | 18/04/2023 | 17/06/2023 | NIRMAL UDYOG | 18.78 | 14.92 | 79.47 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04616/2023-2024 | BP-2023-24-477 | 02/02/2024 | 02/02/2024 | WBSEDCL | 3.33 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of DAULATPUR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4918) [TSM/016355]. | AE SWSD-II | JE3 | ORD/000763/2022-2023 | 3638/SWD-I | 27/03/2023 | 01/10/2025 | PROJECT AND MAINTENANCE | 300.71 | 140.58 | 46.75 | 80
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-I,AE SWSD-II | JE-2,JE1,JE2,JE3,JE4 | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 08/07/2025 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 0 | 35
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Layiing of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, land development, approach road, protection of pipeline and road restoration for DOULATPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/13780) | AE SWSD-II | JE3 | ORD/000290/2024-2025 | 3106/SWD-I | 09/07/2024 | 28/10/2025 | PROJECT AND MAINTENANCE | 188.62 | 0 | 0 | 35
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Miscellaneous works in the interest of maintaining proper operational condition at P.H. No. - 1 under Doulatpur Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/13780) | Assistant Engineer -II | Junior Engineer | ORD/000536/2024-2025 | 1037/AE-II-SMD | 13/08/2024 | 28/08/2024 | SOMNATH ENTERPRISE | 0.78 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based DAULATPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected | SM/13780 | Augmentation | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Doutalpur Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/13780] | Assistant Engineer -II | Junior Engineer | ORD/000832/2024-2025 | 542-AE-II-SMD | 10/05/2024 | 25/05/2024 | AHALYA ENGINEERING WORKS | 0.56 | 0 | 0 | 100
Total | [13 empty] | 1151.22 | 182.46 | 15.85