## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/13781 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Uttar Mohanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000406/2022-2023 | 3804/SMD | 29/12/2022 | 29/03/2023 | KAMAKHYA ENTERPRISE | 22.35 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/13781 | Augmentation | Preparation and submission of Detailed Project Report of "UTTAR MOHANPUR Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000883/2022-2023 | 411/SWD-I | 20/05/2022 | 04/06/2022 | GEO SOLUTION | 2.9 | 2.7 | 93.23 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/13781 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 630 | 19/05/2023 | 19/05/2023 | Resource Division | 24.89 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/13781 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR MOHANPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13781] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000623/2022-2023 | 3239/SWD-I | 01/03/2023 | 19/09/2025 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/13781 | Augmentation | Construction of 300 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of UTTAR MOHANPUR MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1742] [TSM/015329] | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000051/2023-2024 | 270/SWD-I | 24/04/2023 | 01/05/2025 | TUMPA ASSOCIATES | 438.46 | 0 | 0 | 30
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based UTTAR MOHANPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/13781 | Augmentation | Construction of Approach road, Development of Land at OHR site for UTTAR MOHANPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas. (SM/13781) | AE RWS, Alipore Division | JE, RWS, DH-II | ORD/000394/2024-2025 | 3642/SWD-I | 20/08/2024 | 19/10/2024 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 17.76 | 0 | 0 | 40
Total | [13 empty] | 538.08 | 2.7 | 0.5