## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bakeswar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000511/2022-2023 | 350/SMD | 09/02/2023 | 10/05/2023 | S.P. CONSTRUCTION | 22.37 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Preparation and submission of Detailed Project Report of BAKESWAR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000422/2021-2022 | 1972/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.66 | 96.66 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 41.75 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of BAKESWAR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2430) [TSM/016358]. | AE SWSD-II | JE3 | ORD/000169/2023-2024 | 966/SWD-I | 08/06/2023 | 06/09/2023 | M/S B.D. ENTERPRISE | 266.82 | 0 | 0 | 28
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Land development of OHR / 1st Tubewell site at Bakeswar PWSS in the Arsenic Affected areas South 24-Pgns. Dist in Bishnupur-I Block under South 24-Parganas W/S Division-I, P.H.E. Dte. (SM/13782) | AE SWSD-II | JE3 | ORD/000711/2024-2025 | 4541/SWD-I | 06/11/2024 | 06/12/2024 | SRIJON ENTERPRISE | 28.8 | 28.66 | 99.49 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-I,AE SWSD-II | JE-2,JE1,JE2,JE3,JE4 | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 08/07/2025 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 0 | 35
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, land development, approach road, pipeline protection and road restoration for BAKESWAR PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/13782) | AE SWSD-II | JE3 | ORD/000656/2024-2025 | 4381/SWD-I | 22/10/2024 | 16/02/2026 | A.K. SIKDAR | 180.08 | 0 | 0 | 12
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BAKESWAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016358] | AE SWSD-II | JE3 | ORD/000579/2022-2023 | 3096/SWD-I | 23/02/2023 | 31/10/2024 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.87 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of BAKESWAR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/016358] (2nd call) | AE SWSD-II | JE3 | ORD/000236/2023-2024 | 1419/SWD-I | 17/07/2023 | 01/03/2025 | NIKHIL SAMADDAR | 18.78 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BAKESWAR Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13782] | AE SWSD-II | JE3 | ORD/000692/2024-2025 | 4487/SWD-I | 30/10/2024 | 19/03/2025 | M/S. SHYAM CONSTRUCTION | 15.53 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Payment of quotation for new service connection at Bakeswar PWSS, PH No-1 under Bishnupur-I Block. Application No- 1008267733 Reference Id- 106861521 Quotation Date-12/12/2024 Memo No- 1008267733/Quot/03 |  |  | BILL/02487/2024-2025 | BP-2024-25-538 | 24/01/2025 | 24/01/2025 | WBSEDCL | 3.65 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed ground water based Bakeswar piped water supply scheme to accommodate FHTC in Bishnupur - I Block under south 24-Pgns W/S division - I, South 24-Pgns district. For Augmentation of SURFACE WATER BASED WATER SUPPLY SCHEME IN THE ARSENIC AFFECTED ARE | SM/13782 | Augmentation | Payment of quotation for new service connection at Bakeswar PWSS, PH No-2 under Bishnupur-I Block. Application No- 1008268253 Reference Id- 106861505 Quotation Date-12/12/2024 Memo No- 1008268253/Quot/03 |  |  | BILL/02486/2024-2025 | BP-2024-25-537 | 24/01/2025 | 24/01/2025 | WBSEDCL | 3.56 | 0 | 0 | 0
Total | [13 empty] | 1141.92 | 31.32 | 2.74